## Summary
Checks | 35
Pass | 0
Pass with note | 0
Fail | 0
Skipped | 0
Not run | 35
Ready for go-live? | Not yet - checks still to run

## Read Me
AMSON - Go-Live Test (short)
35 checks covering every module, about 3-4 hours for one person or about 1 hour split across 4 people (one section group each). Test on https://amson-web-app.web.app.
How to mark
Pass - works. Pass with note - works but something small looks off (write it in Notes). Fail - doesn't work (write what happened). Skipped - couldn't test (say why).
A 'Pass with note' is fine for go-live; only a 'Fail' needs fixing first. Send any Fail with its number (e.g. Q12) and what you saw.
Before you start
- One browser (or browser profile) per role: Customer, Sales Staff, Technical Staff, Branch Manager. Use real inboxes - codes are emailed.
- Add 2-3 products with stock first (test Q21 and Q23 do this), including one Rx product.
- Afterwards, clear the test data from Settings -> Clear Test Data (before November 15).
The full plan (490 checks) is in AMSON-Test-Plan.xlsx if you have more time.

## Checks
# | Area | Log in as | Do this | Should happen | Req | Result | Tester | Notes
Q01 | 1 Getting in | Branch Manager | Open https://amson-web-app.web.app on a laptop and on a phone. | Shop home loads on both; padlock (https) shows. | REQNF010, REQNF003 | Not run
Q02 | 1 Getting in | Guest | Register a customer with a real email; enter the 6-digit code. | Account created; code arrives; lands in the shop signed in. | REQ001-002 | Not run
Q03 | 1 Getting in | Guest | Wrong password 5 times on one email, wait 2 minutes, log in. | Locked for 2 minutes, then works. | REQ004 | Not run
Q04 | 1 Getting in | Branch Manager | Log in as BM, Technical Staff and Sales Staff (one browser each). | BM/Technical land on Dashboard; Sales Staff on POS. | REQ043, REQ121 | Not run
Q05 | 1 Getting in | Sales Staff | As Sales Staff, type admin/dashboard.html in the address bar. | 'No access' message, then back to POS. | REQNF011 | Not run
Q06 | 2 Shop | Guest | Browse: pick a category, set a price range, choose 'In stock only', sort by price, search a name. | Results match each filter; 'No products found' when nothing matches. | REQ009-012 | Not run
Q07 | 2 Shop | Customer | Add 2 products to the cart, change quantity, remove one. | Totals update straight away. | REQ014-016 | Not run
Q08 | 2 Shop | Customer | Checkout with an address and a delivery schedule; pay with a screenshot + reference no. | Order shows 'Pending Verification' in My Orders; bell + email confirm it. | REQ017-030 | Not run
Q09 | 2 Shop | Customer | Rx product: checkout and pay with a prescription photo. | Pick-up only; 'Pending Prescription Verification'. | REQ021-024 | Not run
Q10 | 2 Shop | Guest | Chat: ask store hours, then 'talk to a person'. | Answer appears; then handed to staff. | REQ035-037 | Not run
Q11 | 3 Orders (staff) | Technical Staff | Payment Verification: approve the normal order. | Payment Confirmed with SI No.; customer notified; stock goes down. | REQ094-102 | Not run
Q12 | 3 Orders (staff) | Technical Staff | Put another order on hold (Underpayment); as the customer, resubmit; approve it. | Hold shows to customer; after approval no 'On Hold' badge remains. | REQ097-098 | Not run
Q13 | 3 Orders (staff) | Technical Staff | Approve the Rx order; also try Reject Prescription with a reason on another. | Ready for Pick-up; rejection reason reaches the customer. | REQ077-079 | Not run
Q14 | 3 Orders (staff) | Technical Staff | Dispatch the paid order with a share.lalamove.com link; as customer mark Received. | Customer sees the tracking link; status Received. | REQ103-105 | Not run
Q15 | 3 Orders (staff) | Technical Staff | Keep Online Orders open while a customer places an order. | New order appears without refreshing; bell count goes up. | REQNF005 | Not run
Q16 | 4 POS | Sales Staff | Sell 2 items for cash; print the receipt. | SI No. on receipt; product list shows the new stock right away. | REQ082, REQ092 | Not run
Q17 | 4 POS | Sales Staff | Sell with G-Cash without a reference no.; then with one. | Blocked, then completes. | REQ082 | Not run
Q18 | 4 POS | Sales Staff | Sell an Rx item without ticking RX Verified; then with it. | Blocked, then completes. | REQ084 | Not run
Q19 | 4 POS | Technical Staff | Void a sale (needs the BM's email + password). | Voided; stock back; shown in Audit Log. | REQ083 | Not run
Q20 | 4 POS | Branch Manager | Keep Inventory open on another computer while the POS sells. | Batch quantity changes on its own. | REQNF005 | Not run
Q21 | 5 Products & stock | Branch Manager | Add a product with prices; change its price with a reason. | Saved; Audit Log shows old price, new price and reason. | REQ068-073 | Not run
Q22 | 5 Products & stock | Technical Staff | As Technical Staff try to change a price. | Price fields locked. | REQ071, REQ120 | Not run
Q23 | 5 Products & stock | Branch Manager | Receive stock with batch and expiry; write off some with a reason. | Stock up, then down; both in Audit Log. | REQ051-063 | Not run
Q24 | 5 Products & stock | Branch Manager | Create a PO, receive it short. | Status Discrepancy; bell alert. | REQ053-057 | Not run
Q25 | 5 Products & stock | Branch Manager | Inventory tabs: Low Stock, Out of Stock, Near-Expiry, Expired. | Each shows the right batches. | REQ066-067 | Not run
Q26 | 5 Products & stock | Technical Staff | Start a stock count, enter counts, submit; finalize as BM with a reason. | Stock adjusted only after BM finalizes. | REQ059-061 | Not run
Q27 | 6 Wholesale | Branch Manager | Add a wholesale buyer with LTO + permit; process an order; download the invoice. | Invoice shows buyer, batch, expiry. | REQ085-092 | Not run
Q28 | 6 Wholesale | Branch Manager | Exchange an item from Purchase History. | EX document; stock moves; Audit Log entry. | REQ090 | Not run
Q29 | 7 Reports & admin | Branch Manager | Reports: Daily Sales for today; download PDF and Excel. | Totals match today's sales; dates MM/DD/YYYY. | REQ111-115 | Not run
Q30 | 7 Reports & admin | Branch Manager | Dashboard: switch Day / Week / Month; export. | Figures change with the period; file downloads. | REQ047 | Not run
Q31 | 7 Reports & admin | Branch Manager | Add a Sales Staff account; deactivate it. | New account works; deactivated one can't log in. | REQ117-119 | Not run
Q32 | 7 Reports & admin | Branch Manager | Audit Log: search, date range, export. | Record / Before / After / Reason columns filled for price, void, write-off. | REQ122-124 | Not run
Q33 | 7 Reports & admin | Branch Manager | Settings: turn on an Announcement banner. | Shows on every shop page. | REQ008 | Not run
Q34 | 8 Phone | Customer | On a phone: browse, cart, checkout, My Orders. | Nothing runs off the screen; buttons tappable. | REQNF003 | Not run
Q35 | 8 Phone | Branch Manager | On a phone: Dashboard, POS, Online Orders. | Usable; sidebar opens from the menu button. | REQNF003 | Not run