## Summary
AMSON - Paper vs. System Deviation Register
Baseline: manuscript dated May 16, 2026 (approved May 22, 2026). System: branch webapp, commit 41f61c8 (2026-10-04).
Reviewed: full manuscript text incl. 4 interview transcripts; Figures 2.2-2.15 (diagrams + text), second full pass of every section incl. tech stack, Gantt, budget, references. Not compared: wireframes 2.16-2.21. The To-Do sheet is the master list.
Status | Requirements | Use-case bubbles
Matches
Partial
Deviates
Missing
Not verified
N/A
Total
Recommendation | Requirements
Change system
Change paper
System + paper
Move to Limitations
Decision needed
Open to-do items
Legend
Matches | System does what the paper says.
Partial | Some of it is built; the rest is missing or different.
Deviates | Built, but behaves differently from the paper.
Missing | Not built.
Not verified | Can't be judged from the code; needs testing.
Change system / Change paper / System + paper | Which side to fix.
Move to Limitations | Keep out of scope, state it in Scope and Limitations.
Decision needed | Too big or a policy choice - the team decides.
Defense risk | How likely the panel hits it: High / Med / Low.
Effort | S = hours, M = about a day, L = several days.

## To-Do
# | Area | Where / refs | Item | Type | Effort | Defense risk | Notes | Paper impact | Owner | Status
1 | Client | Client items (-) | Get from the client: the QR Ph image, the sales invoice format, and the store details for the footer (hotline, email, hours, address, FDA LTO No. - fill js/store-info.js); have them review the Terms/Privacy text. Ask them: are all sales VAT-exempt (sample shows VATable 0.00), is pay-in/pay-out used, who tracks credit collections, which categories to use, may we load the real catalog for the demo? | Manuscript pass | S | High |  | None |  | Open
2 | System | REQ035-038, REQ108-110, REQNF008, REQNF012 | Live chat (guest/customer widget, staff console, resolve threads; AI replies) | Missing | L | High | DECIDED: build it on Gemini via Firebase AI Logic (free tier), swappable to Groq; FAQ answers without AI calls; staff handoff when the free limit is hit. Verify the project's limit in AI Studio first. Decide: build (AI needs a server function) or scope down + Limitations. Affects Objective 1, Scope, Comparative Analysis. | None |  | Open
3 | Decision | Comparative Analysis (p.18) | The proposed system gets a tick for 'AI-powered live chat'; keep only if chat is built. | Manuscript pass | S | High |  | None |  | Open
4 | System | REQ066, Title, Obj. 2 | Near-expiry stock removed from sale by date on every sale/catalog load, not only when Inventory is opened | Partial | S | High | DONE e1e200b. Title feature. | None |  | Done
5 | System | REQ058, REQ111-115, REQNF020, Obj. 3 | Build the Reports module: daily sales (per customer, items with batch + expiry), monthly inventory + purchases (batch, expiry, date received, receipt no., supplier), pull-out, discrepancy; date range; PDF + Excel. Wire the 5 blank Export buttons to it. | Partial | L | High | PARTIAL aece0e7: all 6 Export buttons now produce real PDF/Excel tables of what's on screen; the client's 4 report formats are still to build. Client's one remaining ask (Interview 4). Build to the 4 client samples (see Report Formats sheet); Excel output must paste cleanly into the main office's own sheets (Interviews 1, 2, 4); daily sales should total by payment method to match the daily cash remittance (Interview 2). | None |  | Open
6 | System | REQ024-025, REQ077-081, C3 | Prescription verification: approve/reject with mandatory reason, 'Ready for pick-up' notification, record who verified, RX filter in the queue | Partial | M | High | DONE 082ec92: RX filter, Reject Prescription with reason (7-day re-upload hold), 'ready for pick-up' notice, verifier recorded + audit. | None |  | Done
7 | System | REQ034, REQ104-105 | Show the Lalamove tracking link to the customer on their order page | Partial | S | High | DONE customer order page shows a 'Track with Lalamove' card once dispatched. | None |  | Done
8 | System | REQ028 | Add the client's real QR PH image (assets/payment-qr.png) | Partial | S | High | Need the image from the client. | None |  | Open
9 | System | REQ010-011 | Wire product search (header box) + add price-range and stock-status filters | Missing | S | High | DONE header search on every shop page -> catalog keyword search (name, generic, brand, description); price range + availability filters. | None |  | Done
10 | System | Purpose p.3; Interviews 1-2 | Stop calling system documents 'Official Receipt': relabel the online PDF (js/orders.js:263) and add 'This is not an official receipt' to all system receipts/invoices | Bug | S | High | DONE e1e200b. Client is not BIR-connected by choice and issues BIR/VAT receipts manually on request. | None |  | Done
11 | System | REQ006, REQNF025, Limitations p.7; Interviews 1-3 | Rewrite Terms & Privacy to the client's actual policies: no refunds (exchange only), no cancellation after payment, 7-day hold then closure with credit kept, delivery fee and failed-delivery fees paid by the customer to the rider, RX pick-up only with original prescription, QR Ph only, Data Privacy Act 2012. Remove 'refunds case-by-case' and 'request deletion' (system only deactivates). Replace placeholder support@amson.ph with a real contact. | Partial | S | High | DONE js/legal-content.js used by the sign-up pop-up and new legal.html; written to the client's policies + Data Privacy Act. CLIENT MUST REVIEW before go-live. Panel may read the Terms during the demo. | None |  | Done
12 | System | Report Formats sheet; REQ111; Interviews 2, 4 | Record which batch (batch no. + expiry) each sold item came from, on every POS, online and wholesale sale | Missing | M | High | DONE e1e200b. Every client report lists batch + expiry per sold line; today FEFO deducts the right batch but the sale doesn't remember which. Blocks the Reports module. | None |  | Done
13 | System | Report Formats sheet (SI# 00008247...); Modules p.43 | One sequential Sales Invoice (SI#) number across walk-in, online and wholesale sales | Missing | S | High | DONE e1e200b. Replaces the separate 'receipt numbers' item; voids reference it. | None |  | Done
14 | System | Report Formats sheet (Payment Method section, Terms of Payment) | Payment method + terms on every sale: Cash, G-Cash/QR Ph, Bank Transfer, Terminal (card), Credit (pay later); add to wholesale orders, which record none today | Partial | S | High | DONE e1e200b. Credit was ₱57,534 of ₱81,181 on the sample day. | None |  | Done
15 | System + paper | REQ083, REQ122, Fig 2.6, Fig 2.14, C4 | Walk-in void: reason, original receipt no., automatic stock restore, optional exchange item + price difference, audit entry; restricted to authorized role | Missing | M | High | DONE 57f4d80: BM/Technical void completed sales from POS Today's Sales or Walk-in Orders: reason, SI No., stock restored to the same batches, exchange note + price difference, audit entry. Still open: second-person approval (client rule) and exchange as a real stock movement. Client's #1 pain point (Interview 4). Client rules: a void needs a second authorized person, not one junior staff member alone; exchange item must be equal or higher value (customer pays the difference, never refunded); restored stock must show online too. | Corrects / rewords |  | Done
16 | System + paper | REQ098, REQ102, C2 | Fix overpayment approval: clear the old hold, send 'Payment confirmed' notification; reword REQ098 | Bug | S | High | DONE e1e200b (system part; REQ098 paper wording still to do). From the first review. | Corrects / rewords |  | Done
17 | System + paper | REQ071, REQ073, REQ120, REQNF011, C8 | Price lock: only Branch Manager sets prices on create/import too; enforce in database rules; add a reason to each price change | Partial | S | High | DONE BM-only prices in the form, batch import and quick-add (others' products saved Inactive + 'Price pending'); reason required and logged; enforced in firestore.rules - PUBLISH THE RULES in the Firebase console. | Corrects / rewords |  | Done
18 | Paper | Removals (Letter) sheet | Letter to the panel: OpenAI -> Gemini (free), Firebase Storage -> Cloudinary, DataTable -> custom tables, password reset via Firebase Auth, overpayment approve-and-credit, corrections to scope/conceptual framework | Paper | S | High | One letter covers all remaining removals; send before the paper edits. | REMOVES / narrows - see Removals (Letter) |  | Open
19 | Paper | Objectives / evaluation (p.5-6, 21-24) | Obj. 4 evaluates with TAM + ISO/IEC 25010, but there is no questionnaire, respondent group, sampling, scale, or statistical treatment yet. The final paper needs the instrument and a results chapter. | Manuscript pass | L | High |  | Corrects / rewords |  | Open
20 | Decision | REQ121 | Sales Staff access: trim to POS + catalog view, or reword REQ121 | Deviates | S | Med | DONE 57f4d80: POS (with Today's Sales) + read-only catalog; lands on POS after login. Orders access was added on purpose on 2026-10-01. | None |  | Done
21 | System | REQNF005 | Live updates without refresh on all order and inventory screens (staff + customer) | Deviates | M | Med | DECIDED (revised): build everywhere to avoid a removal letter. | REMOVES / narrows - see Removals (Letter) |  | Open
22 | System | REQNF010, REQNF013 | Deployment: Firebase Hosting (HTTPS) or move hosting to Limitations | Missing | S | Med | DECIDED: Netlify (already set up). | None |  | Open
23 | System | Report Formats sheet (Discount/Deductions columns); Interview 2 | Discount / deduction per sale or line, with reason and audit entry | Missing | M | Med | Client confirmed: no discounts. Not in the paper; client gives boss-approved discounts today. | None (not in paper) |  | Dropped
24 | System | Methodology p.30 ('actual client data'); Report Formats sheet | Load the client's real March-end catalog (prices, batches, expiry) from their workbook via the existing upload templates | Missing | M | Med | DECIDED: yes, once the client sends the catalog. Makes the demo and the TAM evaluation realistic; check confidentiality with the client first. | None |  | Blocked
25 | Decision | Limitations (p.7) | 'Retail item exchanges ... coordinated through live chat': if chat is cut, change this to phone/Messenger. | Manuscript pass | S | Med |  | None |  | Open
26 | Decision | Limitations (p.7) | Add new limitations if decided: hosting/deployment, live chat/AI, real-time refresh, OpenAI cost. | Manuscript pass | S | Med |  | None |  | Open
27 | Decision | Technical Background (p.35, 37) | Netlify listed for hosting with continuous integration; nothing is deployed (Netlify blocked by billing). Depends on the hosting decision. | Manuscript pass | S | Med |  | None |  | Open
28 | System | - | Remove or lock the Migrate Credit page (re-running it re-grants spent credit) | Bug | S | Med | DONE d9fc96b: locks itself after one run; SI counter now staff-only in rules (publish rules). From the first review. | None |  | Done
29 | System | REQ002 | Close the email-verification bypass (code readable by customer; customer can set emailVerified) | Bug | S | Med | From the first review. | None |  | Open
30 | System | REQ005, REQ044, Fig 2.3, Fig 2.8 | Unrecognized-device OTP for customers and staff | Missing | M | Med |  | None |  | Open
31 | System | REQ086, REQ089, REQ091, REQ092 | Wholesale: purchase history per account (with reorder from a past order), wholesale sales invoice, free-of-cost option with reason, document expiry dates | Partial | M | Med | DONE 5cad255: history, sales invoice PDF, free-of-cost, LTO/permit validity. Not built: reorder from a past order. Interview 1: free RX goods go only to medical doctors/hospitals; vitamins open to all. Interview 2: reorder what they bought weeks ago. | None |  | Done
32 | System | REQ090, REQ114, Fig 2.15 | Wholesale exchange workflow (return + FEFO replacement + audit + exchange document) | Missing | M | Med |  | None |  | Open
33 | System | REQ067, C7 | 2-month Bad Order: auto-flag, disposal alert, auto-deduct with write-off record | Missing | M | Med |  | None |  | Open
34 | System | Fig 2.6 Print Transaction Receipt, Modules p.44 | Receipt printing (thermal 58mm print layout) for POS sales | Missing | S | Med | DONE 57f4d80: Print button on every POS receipt; 58mm print layout. The 'not an official receipt' line was removed from POS and online receipts on 2026-10-21 at the team's request. | None |  | Done
35 | System | REQ084 | POS: RX Verified checkbox + optional notes | Missing | S | Med | DONE 57f4d80: checkbox + notes, required for RX items, saved on the sale. | None |  | Done
36 | System | REQ061, C5 | Reconciliation: Branch Manager-only finalize + variance reason in audit log | Partial | S | Med | DONE 06574da: others save counts; BM finalizes; variance reason required and logged. | None |  | Done
37 | System | REQNF025, REQNF029 | Remove dead links and filler: Live Chat sidebar link, chat buttons, footer sample text, footer Privacy/Terms links | Polish | S | Med | DONE footer rebuilt from js/store-info.js (real About text, links to legal.html; contact/LTO lines hidden until the client confirms them); chat links hidden until chat is built; payment page Terms link fixed. From the first review. | None |  | Done
38 | System | REQ039, REQ042 | Email notifications for key order events + on/off toggle in Account Settings | Partial | M | Med | EmailJS free tier: 200/month. | None |  | Open
39 | System | REQ122 | Audit log completeness: structured before/after, reasons, more events (receiving, PO, product create/delete, RX verification) | Partial | M | Med |  | None |  | Open
40 | System | REQ014 | Save cart to the customer's account | Deviates | S | Med | DONE 77336f3. | None |  | Done
41 | System | REQNF003, REQNF007 | Phone/tablet and cross-browser test pass | Not verified | S | Med |  | None |  | Open
42 | System | Interviews 2, 4 | Supplier receipt / DR number field on Receive Stock and PO receiving | Missing | S | Med | DONE e1e200b. Required column in the monthly purchases report. | None |  | Done
43 | System | Interview 4 walkthrough | Supplier history: everything received from each supplier | Missing | S | Med | Shown to the client during the prototype walkthrough. | None |  | Open
44 | System | Methodology p.30; Interview 4 | User manual + hands-on training + handover to the branch | Missing | M | Med | Client: 'kailangan pa namin gamayin, i-hands on pa namin to'. | None |  | Open
45 | System | Report Formats sheet (Customer File shows named walk-ins, e.g. EMPLOYEE) | Optional customer name on walk-in sales (default 'Walk-in') | Missing | S | Med | DONE e1e200b. Customer File groups every sale by customer name. | None |  | Done
46 | System | Report Formats sheet (Supplier sheets) | Unit cost, supplier receipt no., brand and pack on each stock receiving entry | Partial | S | Med | DONE e1e200b: unit cost + receipt/DR no. added; pack size stays in the product name as the branch does today. Monthly purchases report needs cost per delivery, not just the product's current costing. | None |  | Done
47 | System | Report Formats sheet (monthly sheets); js/products-data.js:401 | Match the client's categories: Generics, Branded, Drugstore (per piece), Medical Supplies, Grocery | Deviates | S | Med | DONE e1e200b: also storefront links/filters now follow Manage Categories. Existing Firebase projects keep their current categories - add the client's in Manage Categories.. Default categories are OTC/Vitamins/Personal Care/Health & Wellness; the monthly report is one sheet per client category. | None |  | Done
48 | System | REQ085, REQ087 | Optional agreed price per wholesale buyer per product, used as default on their orders | Partial | M | Med | Keeps per-account pricing (no letter). | REMOVES / narrows - see Removals (Letter) |  | Open
49 | System | Production readiness | Cut database reads: stop loading whole collections on every page (Firestore free-plan daily read cap ~50k) | Partial | M | Med | Needed before real use with the client's ~1,000-product catalog. | None |  | Open
50 | System | Dashboard module p.40; Interview 4 (dashboard export) | Dashboard Sales Analytics: show which dates the Today/Week/Month/Year view covers, and add a picker to choose a specific day, week, month or year (with previous/next) | Missing | S | Med | Requested by the team 2026-10-21. Chart, totals and the export should all follow the picked period, and the export title should name it. | None |  | Open
51 | System | Project Context (p.1) | Says the old POS couldn't print batch numbers, expiration dates or supplier details on receipts. The new receipts don't show them either; add batch/expiry to receipts and reports, or soften the sentence. | Manuscript pass | S | Med |  | None |  | Open
52 | System | Theoretical Framework (p.24) | 'Only authorized branch managers can ... override automated inventory counts': needs the REQ061 fix (Branch Manager-only reconciliation finalize). | Manuscript pass | S | Med | DONE 06574da: system now matches (BM-only finalize). | None |  | Done
53 | System | Conceptual Framework (Output) (p.27) | 'Terms and Conditions remain available throughout the session': footer Privacy/Terms links are dead. Link them to the existing legal text. | Manuscript pass | S | Med | DONE footer links to legal.html on every page. | None |  | Done
54 | System + paper | Modules: Staff roles (p.45-46) | Lists 'void authorization' for Branch Manager and Technical Staff: needs the void feature. 'Sales Staff: product catalog viewing only': see REQ121 decision. | Manuscript pass | S | Med | DONE 57f4d80: void built for BM/Technical; Sales Staff POS-only. | Corrects / rewords |  | Done
55 | Paper | REQ007 / Technical Background p.35-36 | Password reset link is sent by Firebase Authentication, not EmailJS. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
56 | Paper | REQ008 p.47; Modules p.38 | Drop 'promotions' unless you plan them; keep 'announcements' (banner to be built). | Paper edit | S | Med | See Contradictions / Paper Edits | REMOVES / narrows - see Removals (Letter) |  | Open
57 | Paper | REQ031 p.50 | Replace status list with: Pending Verification, Payment Confirmed, Dispatched / Ready for Pick-up, Delivered, Received / Picked Up, On Hold (with type), Closed (Unresolved). | Paper edit | S | Med | See Contradictions / Paper Edits | REMOVES / narrows - see Removals (Letter) |  | Open
58 | Paper | REQ073 p.55 | Add 'and the stated reason' (client requirement, Interview 2) - after the reason field is built. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
59 | Paper | REQ083 p.56; Fig 2.6 text p.73; Fig 2.14 text p.89 | Void applies to completed transactions, referencing the original receipt number (C4). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
60 | Paper | REQ085, REQ087 p.57; Modules p.44 | Default wholesale price per product, adjustable per order (C9). | Paper edit | S | Med | See Contradictions / Paper Edits | REMOVES / narrows - see Removals (Letter) |  | Open
61 | Paper | REQ095, REQ098 p.58-59; Fig 2.6 text p.74; Fig 2.11 text p.83 | Overpayment is approved and the excess is added to the customer's store credit; three hold types plus overpayment-approval (C2). | Paper edit | S | Med | See Contradictions / Paper Edits | REMOVES / narrows - see Removals (Letter) |  | Open
62 | Paper | REQ105 p.60; Fig 2.4 text p.71; Modules p.39-40 | Delivered is set by staff (or automatically after 3 days); the customer's confirmation marks it Received (C1). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
63 | Paper | REQ121 p.61 | Only if you keep Sales Staff access to Walk-in Orders history: add it to REQ121. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
64 | Paper | Fig 2.2 text p.67 | Audit log is available to Technical Staff and Branch Manager (C6). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
65 | Paper | Fig 2.2 diagram | Connect 'Manage Live Chat' to Technical Staff; add missing bubbles or label as summary (C11); one name for the pre-order use case (C12). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
66 | Paper | Fig 2.5 text p.72 | Technical Staff opens/counts; Branch Manager finalizes (C5). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
67 | Paper | Fig 2.2 / 2.7 diagrams | Overpayment, free-of-cost distribution: no bubble anywhere; add 'Record Free-of-Cost Distribution' under Manage Wholesale Accounts if REQ091 stays. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
68 | Paper | Fig 2.8 diagram + text p.76-77 | Add reCAPTCHA, locked-account check, deactivated-account check, unverified-email redirect; make the wrong-OTP path match the text (C13). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
69 | Paper | Fig 2.9 diagram + text p.78-79 | Terms accepted before submit, duplicate email caught at account creation (C14); add Resend Code; end at the shop, signed in (C10). | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
70 | Paper | Fig 2.10 diagram | Move the RX decision to the start of checkout; RX skips the address; add Upload Prescription Photo (C15); optionally add delivery schedule and store credit. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
71 | Paper | Fig 2.11 diagram + text p.82-83 | Prescription approval/rejection before confirmation (C3, after it is built); RX skips courier steps (C17); resolved holds return to admin review (C18); stock shortage -> Out of Stock hold (C19); overpayment approved with credit (C2); expired holds closed by the System lane, credit kept. | Paper edit | S | Med | See Contradictions / Paper Edits | Corrects / rewords |  | Open
72 | Paper | Title page / cover (i) | Still labelled 'Capstone Project Proposal' dated May 16, 2026; update the label and date for the final manuscript. | Manuscript pass | S | Med |  | Corrects / rewords |  | Open
73 | Paper | Whole paper (-) | About 100 'will ...' sentences are written as a proposal. Ask the adviser whether the final manuscript should switch to past/present tense, then convert. | Manuscript pass | M | Med |  | Corrects / rewords |  | Open
74 | Paper | Comparative Analysis (p.18) | The three compared systems are named but not cited in that section: J1TEK = Binag et al. (2024), Online Transporter = Llorente et al. (2022), Bandung FEFO = Malasari & Sudrajat (2023). Binag and Llorente are in the reference list but cited nowhere in the text. | Manuscript pass | S | Med |  | Corrects / rewords |  | Open
75 | Paper | Conceptual Framework (Input) (p.25) | Says wholesale buyers' info is captured during account registration and that wholesale purchase orders are submitted through the platform. Wholesale buyers don't register or order online; staff record them. | Manuscript pass | S | Med |  | REMOVES / narrows - see Removals (Letter) |  | Open
76 | Paper | Methodology: sprint plan (p.30-35) | Phases promise features that aren't built (device OTP, notifications by email, thermal printing, live chat, reports). Align with final decisions. | Manuscript pass | S | Med |  | Corrects / rewords |  | Open
77 | Paper | Calendar of Activities (p.96-98) | Lists a 'Fifth Interview', but the appendices only have four transcripts (J-M). Add the transcript and proof, or remove the row. | Manuscript pass | S | Med |  | Corrects / rewords |  | Open
78 | Paper | Calendar of Activities (p.96-98) | Month header has no year. Update the bars to actual dates. The webapp branch history starts 2026-08-31 (earlier work isn't in this git history), so the team needs to fill earlier dates. | Manuscript pass | S | Med |  | Corrects / rewords |  | Open
79 | System | REQ088 | Hide costing/wholesale prices from public reads | Partial | M | Low | DECIDED (revised): build it to avoid a removal letter. | None |  | Open
80 | System | Interview 1 | Park/hold a walk-in sale ('keep') while serving the next customer | Missing | M | Low | DECIDED: future work. Client's current POS practice; not in the paper. | None (not in paper) |  | Dropped
81 | System | Report Formats sheet (CREDIT terms) | Credit sales follow-up (who owes what, mark as paid) | Missing | M | Low | DECIDED: future work. Not in the paper; ask the client if the main office tracks collections instead. | None (not in paper) |  | Dropped
82 | System | Report Formats sheet (daily Sales section) | Pay-in / pay-out (cash drawer in and out) recorded per day | Missing | S | Low | DECIDED: future work. Both were 0.00 on the sample day; ask if it's used. | None (not in paper) |  | Dropped
83 | Decision | Technical Background (p.35) | States the AI assistant won't give medical advice: keep only if chat is built. | Manuscript pass | S | Low |  | None |  | Open
84 | System | REQ013, REQ068 | Dosage/usage notes field on products | Missing | S | Low | DONE 06574da. | None |  | Done
85 | System | REQ049 | Supplier column in the inventory batch table | Partial | S | Low | DONE 06574da. | None |  | Done
86 | System | REQ103, REQ107 | Delivery: 'copy all' including preferred schedule + order no.; internal delivery notes | Partial | S | Low | DONE 06574da. Use the notes for rider name/plate/number, which staff currently screenshot privately (Interviews 2-3). | None |  | Done
87 | System | REQ116 | Customer Accounts: list of the customer's orders | Partial | S | Low | DONE 847c877. | None |  | Done
88 | System | REQ118 | Staff creation uses shared validators; stop silent Administrator -> Branch Manager change | Bug | S | Low | DONE 847c877. From the first review. | None |  | Done
89 | System | REQ070 | Category rename: replace native prompt() with app dialog | Polish | S | Low | DONE category tools commit: rename uses the app dialog; deleting a category can move its products. From the first review. | None |  | Done
90 | System | REQ033, REQ093 | Receipt only after verification; show subtotal/credit applied on PDF | Partial | S | Low | DONE 082ec92. From the first review. | None |  | Done
91 | System | REQ099 | 'Payment not received' as its own hold type | Partial | S | Low | DONE 847c877. | None |  | Done
92 | System | REQ026 | Checkout pick-up notice mentions bringing the original prescription | Partial | S | Low | DONE 082ec92. | None |  | Done
93 | System | REQ009 | Show quantity in stock on catalog cards | Partial | S | Low | DONE 06574da. | None |  | Done
94 | System | REQ040 | Profile picture in Account Settings | Missing | S | Low | DONE 77336f3. | None |  | Done
95 | System | REQNF028 | One date formatter (MM/DD/YYYY, 12-hour) across all screens | Partial | S | Low | DONE 847c877. | None |  | Done
96 | System | REQ047 | Dashboard 'Active Online Orders' excludes delivered/closed | Bug | S | Low | DONE d9fc96b: counts verified + dispatched only. From the first review. | None |  | Done
97 | System | REQNF017 | README with setup steps; fix the error message that points to it | Missing | S | Low | DONE 77336f3. From the first review. | None |  | Done
98 | System | REQ001 | Normalize phone number at registration | Bug | S | Low | DONE d9fc96b. From the first review. | None |  | Done
99 | System | REQ008; Interview 1 | Store announcements + promotions banner, editable by staff (e.g. closure days) | Missing | S | Low |  | None |  | Open
100 | System | REQ031 | Show invalid-payment holds to customers as 'Payment Rejected - re-upload needed' | Partial | S | Low | DONE d9fc96b: customer badges show Payment Rejected / Balance Due / Out of Stock / Prescription Rejected. Keeps the paper's status name (no letter). | None |  | Done
101 | System | Technical Background p.35-37 | Inventory movement chart on the dashboard (stock in/out over the period) | Missing | S | Low | Keeps the Chart.js claim (no letter). | None |  | Open
102 | System | Modules p.42 | Price lock/unlock toggle per product (Branch Manager only) | Missing | S | Low | DONE Lock/Unlock prices button for the Branch Manager in Edit Product. Keeps 'price locking' (no letter). | None |  | Done
103 | System | Theoretical Framework p.23 | Browser notifications for staff alerts (new order, pending payment, expiry, low stock) | Missing | S | Low | Keeps the 'push notifications' claim (no letter). | None |  | Open
104 | System | REQ039, Fig 2.10, C16 | Order-placed notification in the customer's bell (no database rule change needed if derived from order status) | Missing | S | Low |  | None |  | Open
105 | System | System roles (-) | The system also has a legacy 'Administrator' role that the paper never mentions. Hide it from the UI or document it. | Manuscript pass | S | Low |  | None |  | Open
106 | System + paper | Whole paper + system (-) | 'QR PH' in the paper and most screens, 'QR Ph' on the payment page image text. The official name is 'QR Ph'; pick one everywhere. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
107 | Paper | Modules FEFO p.41 | Add the 2-month Bad Order step (C7). | Paper edit | S | Low | See Contradictions / Paper Edits | Corrects / rewords |  | Open
108 | Paper | Technical Background p.35-37; Budget p.99 | Cloudinary instead of Firebase Storage; Choices.js added; DataTable removed; hosting per decision (Tech Stack sheet). | Paper edit | S | Low | See Contradictions / Paper Edits | REMOVES / narrows - see Removals (Letter) |  | Open
109 | Paper | Scope p.6; Product Browsing REQ009 | The client also sells medical supplies and grocery items (monthly report); the paper only mentions OTC/prescription medicines. Mention them, or exclude them on purpose. | Paper edit | S | Low | See Contradictions / Paper Edits | Adds |  | Open
110 | Paper | Scope and Limitations p.7 | Add: system receipts/invoices are internal records, not BIR-registered official receipts; BIR/VAT receipts stay manual on request; no BIR or government integration (client policy, Interview 1). | Paper edit | S | Low | See Contradictions / Paper Edits | Adds |  | Open
111 | Paper | Decision-dependent | Live chat/AI (Obj. 1, Scope, Framework, REQ035-038, REQ108-110, NF008, NF012); real-time refresh (NF005); hosting (NF013); wholesale price visibility (REQ088). | Paper edit | S | Low | DECIDED: build it on Gemini via Firebase AI Logic (free tier), swappable to Groq; FAQ answers without AI calls; staff handoff when the free limit is hit. Verify the project's limit in AI Studio first. See Contradictions / Paper Edits | Corrects / rewords |  | Open
112 | Paper | Whole paper (-) | Spelling consistency: 'Fulfilment' on the cover vs 'fulfillment' elsewhere. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
113 | Paper | Scope (p.6) | 'Intended to serve retail customers, wholesale clients, branch staff, and main office management': wholesale clients and the main office never log in. Reword to 'staff record wholesale transactions; reports are submitted to the main office'. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
114 | Paper | Theoretical Framework (p.22-23) | Mentions 'instantaneous push notifications for near-expiry supplies'; the system has an in-app notification bell, not push notifications. Reword. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
115 | Paper | Methodology: sprint plan (p.32) | Phase 4 (customer side) lists the 'one-click copy feature for delivery details' under My Orders; that's an admin Delivery feature (also listed in Phase 6). Remove it from Phase 4. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
116 | Paper | Technical Background (p.35) | Say 'Cloud Firestore' instead of 'real-time database', and Cloudinary instead of Firebase cloud storage for images. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
117 | Paper | Technical Background (p.35-36) | EmailJS listed for order confirmations and password reset links: password reset is Firebase Auth; order emails depend on REQ039. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
118 | Paper | Technical Background (p.35-36) | Chart.js listed for 'inventory movement data': dashboard charts are sales only (inventory uses count tiles). Reword or add an inventory chart. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
119 | Paper | Technical Background (p.35, 37) | DataTable listed; tables are custom-built. Remove or reword. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
120 | Paper | Technical Background: Software (p.36-38) | Missing tools actually used: Cloudinary (images), Choices.js (searchable dropdowns), Bootstrap Icons, Google Fonts (Roboto), Git/GitHub (version control), Node.js http-server (local serving). | Manuscript pass | S | Low |  | Adds |  | Open
121 | Paper | Technical Background: Software (p.38) | Canva is listed for mockups, but the Gantt chart says 'Creation of Figma'. Use one tool name. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
122 | Paper | Modules: Price Management (p.42) | 'Allows price locking': the lock is the Branch Manager-only rule (no separate lock switch). Reword, or add a lock toggle. | Manuscript pass | S | Low |  | REMOVES / narrows - see Removals (Letter) |  | Open
123 | Paper | Wireframes (Figs 2.16-2.21) (p.92-95) | Not compared yet. Replace with real screenshots, or keep them labelled as early wireframes. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
124 | Paper | Calendar of Activities (p.97-98) | Add rows for work actually done (POS, inventory, payment verification, wholesale, reports, testing) and mark 'System Deployment' per the hosting decision. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
125 | Paper | Budgetary Estimate (p.99) | Total ₱31,790.08 checks out. Missing: Cloudinary (free), OpenAI API (pay-per-use, if chat is built), thermal printer (if printing is in scope). | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
126 | Paper | Budgetary Estimate (p.99) | Domain name ₱841.08 and Firebase Blaze ₱200: keep only if actually bought/used. Netlify is listed as free, but deployment was blocked by billing; make these consistent. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
127 | Paper | References (p.100) | Davis reference is written 'Fred D. Davis. (1989)'; APA is 'Davis, F. D. (1989).' | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
128 | Paper | References (p.10 / refs) | 'The Generics Pharmacy (TGP) Sumulong Case Study (2024)' is cited without an author; check the APA author/organization format. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
129 | Paper | References (p.17 / refs) | Sardjono et al. (2023) is described as an Agile-based study, but its listed title is about Track and Trace in Pharma 4.0. Verify the source matches the summary. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
130 | Paper | Appendices (p.124) | List of Appendices says 'PayMongo Pricing' / 'Lalamove API Instruction'; the appendix pages say 'PayMongo Pricing Limitation' / 'Lalamove API Limitation'. Match titles. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open
131 | Paper | Table of Contents / List of Figures (p.iv-vi) | Regenerate page numbers after all edits. | Manuscript pass | S | Low |  | Corrects / rewords |  | Open

## Requirements
ID | Module | Paper says (summary) | Status | Evidence (file:line) | What differs | Recommendation | Reason | Defense risk | Effort | Paper / source ref
REQ001 | Registration/Login | Register with full name, email, contact no., password | Matches | js/register.js:140 | - | None |  | Low | - | p.46
REQ002 | Registration/Login | Email verification code; activate only after verification | Partial | js/register.js:214; js/verify-email.js:94; firestore.rules:43 | Works, but the code is stored on the customer's own user doc (readable by them) and the rules let a customer set emailVerified:true themselves, so verification can be bypassed. | Change system | Panel security question risk; small rules + storage change. | Med | S | p.46
REQ003 | Registration/Login | CAPTCHA on registration and login | Matches | js/register.js:184; js/auth.js:111 | - | None |  | Low | - | p.46
REQ004 | Registration/Login | Lock account 2 min after 5 failed logins | Matches | js/auth.js:57 | Lockout counter lives in a public loginAttempts collection anyone can reset (firestore.rules loginAttempts). | None | Behaviour matches; weakness is acceptable for capstone, mention if asked. | Low | - | p.46
REQ005 | Registration/Login | Email OTP when logging in from an unrecognized device | Missing | - | No device recognition or login OTP exists. | Change system | Also in Fig 2.3 (Verify OTP) and Activity 2.8; OTP + EmailJS code already exists (js/otp.js) to reuse. | Med | M | p.46; Fig 2.3; Fig 2.8
REQ006 | Registration/Login | Show Terms and Conditions; require acceptance | Matches | js/terms-gate.js:34 | Terms rewritten to the branch's policies (client to review). (was: -) | None |  | Low | - | p.46
REQ007 | Registration/Login | Password recovery via time-limited reset link | Matches | js/forgot-password.js:51 | Sent by Firebase Auth, not EmailJS as the Technical Background says. | Change paper | Tech wording only (see Tech Stack sheet). | Low | - | p.47
REQ008 | Home | Home page with products, announcements, promotions, navigation | Partial | shop/index.html | Featured products and categories exist; no announcements or promotions section. | Change system | The client announces store closures (e.g. long weekends) to buyers today (Interview 1); a simple staff-editable announcement banner covers it. Promotions can be dropped from the paper. | Low | S | p.47; Interview 1
REQ009 | Product Browsing | Catalog by category with name, price, stock availability | Matches | js/products-data.js:696 | 06574da: catalog cards show the quantity in stock. (was: Cards show name/price and an Out of Stock badge, but not the quantity available (only on the product page).) | None | One-line card change. | Low | S | p.47
REQ010 | Product Browsing | Filter by category, price range, stock status | Matches | js/products.js:31; shop/products.html | Fixed: price range + availability filters. (was: Category filter and price sort only; no price-range or stock-status filter.) | None | Small UI addition; visible in demo. | Med | S | p.47
REQ011 | Product Browsing | Keyword / product-name search | Matches | shop/products.html:38 (input has no handler) | Fixed: header search works on every page. (was: Header search box is not wired to anything on any page.) | None | Panel will type in it; small fix. | High | S | p.47; Fig 2.3 Filter and Search
REQ012 | Product Browsing | 'No products found' message | Matches | js/products.js:70 | - | None |  | Low | - | p.47
REQ013 | Product View | Product page: name, description, price, stock, dosage/usage notes, images | Matches | js/product-details.js | 06574da: Dosage / Usage notes field shown on the product page and quick view. (was: No dosage/usage notes field exists anywhere.) | None | Add one optional field to product form + page. | Low | S | p.47
REQ014 | Cart | Persistent cart per logged-in customer | Matches | js/cart.js:5 (localStorage) | 77336f3: signed-in cart saved on the account and merged with any guest cart at sign-in. (was: Cart is stored in the browser, so it follows the device, not the account.) | None | Activity 2.10 says cart persists across sessions; small sync to users/{uid}. | Med | S | p.47; Fig 2.10
REQ015 | Cart | Adjust quantities / remove items | Matches | js/cart-page.js:40 | - | None |  | Low | - | p.48
REQ016 | Cart | Running total updates on change | Matches | js/cart-page.js | - | None |  | Low | - | p.48
REQ017 | Checkout | Collect delivery address before submission | Matches | js/checkout.js:140 | - | None |  | Low | - | p.48
REQ018 | Checkout | Save default delivery address | Matches | js/checkout.js:164 | Saved automatically on every checkout rather than as an explicit choice. | None | Acceptable. | Low | - | p.48
REQ019 | Checkout | Block submission without address | Matches | shop/checkout.html (required fields) | - | None |  | Low | - | p.48
REQ020 | Checkout | Notice: delivery fee paid to Lalamove rider | Matches | shop/checkout.html:177; shop/payment.html:196 | Payment page says pay rider 'cash'; interview 3 says riders also take GCash. | Change system | Copy tweak only. | Low | S | p.48; Interview 3
REQ021 | Prescription Pre-Order | RX pre-order requires prescription photo | Matches | js/payment.js:38 | - | None |  | Low | - | p.48
REQ022 | Prescription Pre-Order | Full QR PH payment + screenshot before submission | Matches | js/payment.js | - | None |  | Low | - | p.48
REQ023 | Prescription Pre-Order | RX pre-orders are pick-up only | Matches | js/checkout.js:63 | - | None |  | Low | - | p.49
REQ024 | Prescription Pre-Order | Submitted as 'Pending Prescription Verification'; not prepared until staff approve the prescription | Matches | js/orders.js:5 | 082ec92: RX orders show 'Pending Prescription Verification' and aren't prepared until staff approve the prescription. (was: RX orders use the same 'Order Pending Verification' status as normal orders; prescription approval is not a separate step.) | None | Paper repeats this in Modules, Conceptual Framework, Fig 2.10; system change is moderate. | High | M | p.49; Fig 2.10
REQ025 | Prescription Pre-Order | Notify approved/ready for pick-up, or rejected with reason | Matches | js/admin-online-orders.js:392 | 082ec92: approval sends 'ready for pick-up'; rejection sends the reason. (was: Approval sends 'Payment confirmed' only; there is no rejection path at all.) | None | Part of the RX verification fix. | High | M | p.49
REQ026 | Prescription Pre-Order | Notice: original prescription must be presented at pick-up | Matches | shop/checkout.html:133 | 082ec92: checkout and payment pages say to bring the original prescription. (was: Checkout pick-up notice does not mention the original prescription (only the later pick-up notification does).) | None | Copy change. | Low | S | p.49
REQ027 | Prescription Pre-Order | Customer can view RX pre-order status in My Orders | Matches | js/orders-list.js | - | None |  | Low | - | p.49
REQ028 | Payment | Show branch QR PH code and account details | Partial | shop/payment.html:135 | Page points to assets/payment-qr.png, which is not in the repo, so customers see a placeholder. | Change system | Needs the client's actual QR image; highly visible in demo. | High | S | p.49
REQ029 | Payment | Require payment screenshot upload | Matches | js/payment.js | - | None |  | Low | - | p.49
REQ030 | Payment | Hold order pending verification until admin confirms | Matches | js/admin-online-orders.js:257 | - | None |  | Low | - | p.49
REQ031 | My Orders | Statuses: pending payment, payment verified, confirmed, dispatched, delivered, payment rejected | Deviates | js/orders.js:5 | System statuses: placed, payment_confirmed, dispatched, delivered, received, closed_unresolved, plus On Hold. No 'payment rejected'. | Change paper | System matches the hold/7-day policy in REQ096-100; update the status list. | Med | - | p.50
REQ032 | My Orders | View full order details | Matches | js/order-details.js:191 | - | None |  | Low | - | p.50
REQ033 | My Orders | View/download system receipt for completed orders | Matches | js/orders.js:247 | 082ec92: receipt only after verification; PDF shows subtotal and store credit applied. (was: Receipt downloadable for any order (even unpaid); PDF shows only final total, not subtotal/credit applied.) | None | Small. | Low | S | p.50
REQ034 | My Orders | Customer monitors delivery progress | Matches | js/order-details.js (no trackingLink) | Fixed: customer sees the Lalamove tracking link. (was: Status timeline shows, but the Lalamove tracking link staff paste is never shown to the customer.) | None | REQ104/105 and Activity 2.11 say the link is 'immediately reflected' to the customer. | High | S | p.50; Fig 2.11
REQ035 | Live Chat | Live chat for guests and customers | Missing | shop/*.html floating-chat-btn href='#' | Buttons exist but go nowhere. | Decision needed | Large feature in objectives, scope, framework and comparative analysis. Options: build it, or scope down and move to Limitations. | High | L | p.50; Obj. 1; Scope
REQ036 | Live Chat | AI-powered responses (OpenAI) for common inquiries | Missing | - | Not built. A browser-only app cannot hide an OpenAI key, so this needs a server function (e.g. Firebase Cloud Functions, Blaze plan). | Decision needed | Same decision as REQ035. | High | L | p.50; NF008; NF012
REQ037 | Live Chat | Escalate to staff when needed | Missing | - | Not built. | Decision needed | Same decision as REQ035. | High | L | p.50
REQ038 | Live Chat | Notify staff of new/escalated chats | Missing | - | Not built. | Decision needed | Same decision as REQ035. | Med | S | p.50
REQ039 | Customer Notification | In-platform and email notifications for order/payment/delivery updates | Partial | js/orders.js:108; js/shop-header.js:54 | In-platform bell works; no email notifications are sent (EmailJS is only used for OTP). No notification at all when an order is placed (Fig 2.10 'Send Order Submission Notification'). | Change system | EmailJS already set up; free tier is 200 emails/month (Budget). | Med | M | p.51; Fig 2.10
REQ040 | Account Settings | Update name, address, contact no., profile picture | Matches | js/account-settings.js:87 | 77336f3: profile photo upload in Account Settings. (was: No profile picture.) | None | Cloudinary upload already exists; small. | Low | S | p.51
REQ041 | Account Settings | Confirm current password before setting new one | Matches | js/account-settings.js:157 | - | None |  | Low | - | p.51
REQ042 | Account Settings | Enable/disable email notifications | Missing | - | No toggle (and no email notifications yet). | Change system | Comes with REQ039. | Low | S | p.51
REQ043 | Admin Login | Staff log in with credentials created by Branch Manager; role permissions applied | Matches | js/auth.js:94; js/admin-staff-management.js:188 | - | None |  | Low | - | p.51
REQ044 | Admin Login | Staff OTP only on unrecognized device | Missing | - | Not built (same as REQ005). | Change system | Do together with REQ005. | Med | M | p.51; Fig 2.8
REQ045 | Admin Login | Staff lockout after 5 failed attempts | Matches | js/auth.js:57 | Shared with customer login. | None |  | Low | - | p.51
REQ046 | Admin Login | Staff password reset link | Matches | js/forgot-password.js:51 | - | None |  | Low | - | p.51
REQ047 | Dashboard | Daily sales, active orders, low stock, near expiry, pending verifications, quick navigation | Matches | js/admin-dashboard.js:129 | Exceeds paper (charts, period filter, out-of-stock). 'Active Online Orders' wrongly counts delivered and closed orders. | Change system | Count fix is one line. | Low | S | p.52
REQ048 | Admin Notifications | Notify BM + Technical of new orders, payments, stock, expiry, wholesale updates, chat | Partial | js/products-data.js:257 | 57f4d80: no longer shown to Sales Staff. Still missing wholesale-order and chat notifications. (was: Covers orders, payments, stock, expiry, PO discrepancies. No wholesale order updates or chat. Also shown to Sales Staff.) | Change system | Wholesale/chat parts depend on those features. | Low | S | p.52
REQ049 | Inventory | Inventory list per product by batch, with supplier details | Matches | admin/inventory.html:153 | 06574da: batch table has a Supplier column (with receipt/DR no.). (was: Batch table has no supplier column.) | None | Data exists (supplierId on batch); add column. | Low | S | p.52
REQ050 | Inventory | Consistent stock across concurrent transactions | Matches | js/products-data.js:606 | Firestore transactions (FEFO multi-item). | None |  | Low | - | p.52
REQ051 | Inventory | Record write-offs | Matches | js/admin-inventory.js:994 | - | None |  | Low | - | p.52
REQ052 | Inventory | Reason required for write-off | Matches | js/admin-inventory.js:994 | - | None |  | Low | - | p.52
REQ053 | Purchase Orders | Create PO: supplier, products, quantities, date; Pending | Matches | js/admin-inventory.js:1442 | - | None |  | Low | - | p.52
REQ054 | Purchase Orders | Link delivery to existing PO when receiving | Matches | js/admin-inventory.js:1548 | Receiving is done from inside the PO. | None |  | Low | - | p.53
REQ055 | Purchase Orders | Auto-compare received vs PO quantities | Matches | js/admin-inventory.js:1548 | - | None |  | Low | - | p.53
REQ056 | Purchase Orders | Discrepancy report + PO status Discrepancy | Matches | js/admin-inventory.js:1548 | Shown on screen per PO; variance is per product (batch is recorded per line). | None |  | Low | - | p.53
REQ057 | Purchase Orders | Received when matched; acknowledgment to close Discrepancy | Matches | js/admin-inventory.js:1657 | - | None |  | Low | - | p.53
REQ058 | Purchase Orders | Discrepancy reports by date range, PDF/Excel | Missing | - | No discrepancy report export. | Change system | Part of the Reports module. | Med | M | p.53
REQ059 | Stock Reconciliation | Input physical counts | Matches | js/admin-inventory.js:1233 | - | None |  | Low | - | p.53
REQ060 | Stock Reconciliation | Auto variance calculation | Matches | js/admin-inventory.js | - | None |  | Low | - | p.53
REQ061 | Stock Reconciliation | Branch Manager finalizes; variance reason in Audit Log | Matches | js/admin-inventory.js:1233 | 06574da: only the Branch Manager finalizes; others save the count; variance reason required and logged with each batch's change. (was: Any staff with Inventory access can finalize; no variance reason is asked or logged (only a count of adjusted batches).) | None | Small role check + reason field. Fig 2.5 shows Technical Staff doing reconciliation - see Contradictions C5. | Med | S | p.53; Fig 2.5
REQ062 | Stock Receiving | Record deliveries: product, qty, batch, expiry, supplier | Matches | js/admin-inventory.js:537 | - | None |  | Low | - | p.54
REQ063 | Stock Receiving | Stock added immediately on confirmation | Matches | js/admin-inventory.js:537 | - | None |  | Low | - | p.54
REQ064 | Batch Upload | Bulk stock upload via Excel/CSV template | Matches | js/admin-inventory.js:727 | Also available for products. | None |  | Low | - | p.54
REQ065 | FEFO | FEFO across all transactions | Matches | js/products-data.js:606 | - | None |  | Low | - | p.54
REQ066 | FEFO | Flag batches within 6 months; remove from sellable; wholesale free-of-cost only | Matches | js/products-data.js:384; js/admin-inventory.js (only caller) | Fixed: retail stock excludes near-expiry batches by date on every load and sale; expired stock never sold. (was: The flag only runs when someone opens the Inventory page. Until then, near-expiry batches stay sellable online and at the POS. Free-of-cost distribution is not a recorded transaction type (see REQ091).) | None | This is the title feature ('Real-Time Expiry Monitoring') and Objective 2; exclude near-expiry batches from sellable stock by date everywhere, not only on that page. | High | S | p.54; Title; Obj. 2
REQ067 | FEFO | Within 2 months: Bad Order, disposal alert, auto-deduct | Missing | - | No 2-month Bad Order handling. | Change system | Client described this exact practice (Interview 1). | Med | M | p.54; Interview 1
REQ068 | Product Management | Create/edit/remove products incl. dosage notes, costing, retail, wholesale, image | Matches | js/admin-products.js:347 | 06574da: dosage notes field added to the product form. (was: No dosage notes field.) | None | Same as REQ013. | Low | S | p.54
REQ069 | Product Management | Supplier records linked to products | Matches | js/admin-suppliers.js:255 | - | None |  | Low | - | p.55
REQ070 | Product Management | Add, rename, remove categories | Matches | js/admin-products.js:713 | Fixed: rename uses the app dialog; delete can move products. (was: Rename uses the browser's native prompt(), the only native dialog left.) | None | Small. | Low | S | p.55
REQ071 | Price Management | Price changes restricted to Branch Manager | Matches | js/admin-products.js:69; js/admin-roles.js:17; firestore.rules:55 | Fixed: BM-only prices everywhere, enforced in database rules (publish rules). (was: Only editing an existing product is locked. Any staff (incl. Sales Staff) can set prices when creating or batch-importing a product, and the database rules let any staff write prices.) | None | Client's core ask ('one person lock', Interviews 1-2). | High | S | p.55; Interviews 1-2
REQ072 | Price Management | Confirm price change before saving | Matches | js/admin-products.js:347 | Confirm step now also asks for a reason. (was: -) | None |  | Low | - | p.55
REQ073 | Price Management | Audit log: previous price, new price, timestamp | Partial | js/admin-products.js:347 | System now logs the reason too; paper REQ073 wording should add 'reason'. (was: Matches the paper, but the client asked for a reason with each change (Interview 2) and none is captured.) | System + paper | Add a reason field and add 'reason' to REQ073. | Med | S | p.55; Interview 2
REQ074 | Order Processing | Searchable, filterable order queue | Matches | js/admin-online-orders.js | - | None |  | Low | - | p.55
REQ075 | Order Processing | Confirm, update, or hold orders | Matches | js/admin-online-orders.js:891 | - | None |  | Low | - | p.55
REQ076 | Order Processing | FEFO deduction on confirmation | Matches | js/admin-online-orders.js:392 | - | None |  | Low | - | p.55
REQ077 | RX Verification | Dedicated RX pre-order queue with prescription + payment proof | Matches | js/admin-online-orders.js:257 | 082ec92: RX filter + RX badge in the verification queue, prescription and payment shown together. (was: RX orders appear in the general Payment Verification queue with the photo shown; no dedicated queue or filter.) | None | Could be a filter/tab rather than a new page. | Med | M | p.55
REQ078 | RX Verification | Approve after checking prescription: FEFO reservation, Ready for Pick-up, notify | Matches | js/admin-online-orders.js:392 | 082ec92: approval reserves stock (FEFO), sets Ready for Pick-up and notifies 'ready for pick-up'. (was: Approving payment moves RX orders straight to Ready for Pick-up, but the notification says 'Payment confirmed', not 'Ready for pick-up'.) | None | Part of the RX verification fix. | Med | S | p.55
REQ079 | RX Verification | Mandatory reason to reject; reason in customer notification | Matches | - | 082ec92: Reject Prescription with required reason + message; customer can re-upload within 7 days. (was: No reject action exists for prescriptions.) | None | Part of the RX verification fix. | High | M | p.56
REQ080 | RX Verification | RX never assignable to delivery | Matches | js/checkout.js:63 | - | None |  | Low | - | p.56
REQ081 | RX Verification | Record staff, timestamp, action per verification | Matches | - | 082ec92: every approval/hold/rejection stores who, when and what (verification field) + audit entry for RX. (was: Who approved is not stored.) | None | Small. | Med | S | p.56
REQ082 | Walk-in Orders | Technical + Sales Staff process walk-in sales (OTC + RX) | Matches | js/admin-pos.js:187 | - | None |  | Low | - | p.56
REQ083 | Walk-in Orders | Void with reason, restore stock, audit log, record exchange + price difference | Partial | - | 57f4d80: void for completed walk-in sales by BM/Technical (Admin too): reason, original SI No., stock back to the exact batches, optional exchange note + price difference, audit entry. Not yet: second-person approval; exchange item is a note, not a stock movement. (was: No void function at all.) | System + paper | Client's #1 stated pain point (Interview 4), plus a use case in Fig 2.6. Paper wording is self-contradictory on timing - see C4. | High | M | p.56; Fig 2.6; Fig 2.14; Interview 4
REQ084 | Walk-in Orders | RX Verified checkbox + optional notes, no upload | Matches | admin/pos.html | 57f4d80: RX Verified checkbox + optional notes in POS, required when the cart has RX items. (was: Not in POS.) | None | Small. | Med | S | p.56; Fig 2.14
REQ085 | Wholesale | Wholesale accounts with contact, business type, agreed pricing | Partial | js/admin-wholesale-accounts.js:270 | No per-account agreed pricing; price comes from the product's wholesale price and can be edited per order. | Change paper | Matches how client described 'special price for wholesalers'; reword REQ085/087. | Low | - | p.57; Interview 2
REQ086 | Wholesale | Upload/update LTO and Business Permit | Matches | js/admin-wholesale-accounts.js:270 | 5cad255: LTO and Business Permit valid-until dates; cards flag expired/expiring; orders blocked while expired. (was: Upload works; no document expiry date or 'expired' flag (shown in Interview 4 walkthrough and Activity 2.13).) | None | Small: add expiry dates + badge. | Low | S | p.57; Fig 2.13; Interview 4
REQ087 | Wholesale | Record wholesale POs linked to account with wholesale pricing | Matches | js/admin-wholesale-accounts.js:473 | - | None |  | Low | - | p.57
REQ088 | Wholesale | Wholesale prices admin-only; not shown on retail site | Partial | firestore.rules:55 | Not displayed, but costing/wholesale prices sit in the public products collection and can be read by anyone. | Decision needed | Moving price fields to a staff-only collection is moderate work. | Low | M | p.57
REQ089 | Wholesale | Purchase history per wholesale account | Matches | - | 5cad255: Purchase History per wholesale account, with invoice download. (was: Orders are saved (wholesaleOrders) but there is no history view.) | None | Client asked for a 'customer file' (Interview 2, 4). | Med | S | p.57; Interview 2
REQ090 | Wholesale | Wholesale item exchanges with FEFO + audit log | Missing | - | Not built. | Change system | Has its own activity diagram (Fig 2.15) and report (REQ114). | Med | M | p.57; Fig 2.15
REQ091 | Wholesale | Free-of-cost near-expiry distributions, zero cost, reason in audit log | Matches | js/admin-wholesale-accounts.js:380 | 5cad255: free-of-cost option (prices 0), required reason, own audit entry, noted on the invoice. (was: A unit price of 0 is possible, but there is no free-of-cost option, reason, or dedicated audit entry.) | None | Small. | Med | S | p.57; Interview 2
REQ092 | Transaction Records | Retail/walk-in receipt; wholesale sales invoice with buyer details | Matches | js/products-data.js:478 | 5cad255: wholesale sales invoice PDF with buyer details, batch and expiry per line; walk-in/online receipts carry SI No. (was: Walk-in and online receipts exist; no wholesale sales invoice. Receipts show no batch numbers or expiry dates, which the Project Context (p.1) names as the old POS's main gap.) | None | jsPDF already used. | Med | S | p.58; p.1
REQ093 | Transaction Records | Receipt on payment verification, downloadable in My Orders | Matches | js/orders.js:247 | 082ec92: receipt only downloadable once payment is verified (SI No. assigned). (was: Available before verification too.) | None | Same fix as REQ033. | Low | S | p.58
REQ094 | Payment Verification | Verification queue of orders with proof | Matches | js/admin-online-orders.js:257 | - | None |  | Low | - | p.58
REQ095 | Payment Verification | Confirm, or hold with issue type | Matches | js/admin-online-orders.js:561 | - | None |  | Low | - | p.58
REQ096 | Payment Verification | On Hold - Invalid Screenshot + notify re-upload | Matches | js/admin-online-orders.js:561 | - | None |  | Low | - | p.58
REQ097 | Payment Verification | On Hold - Underpayment, record outstanding, notify | Matches | js/admin-online-orders.js:561 | - | None |  | Low | - | p.58
REQ098 | Payment Verification | On Hold - Overpayment, excess as unapplied value | Deviates | js/admin-online-orders.js:638 | System approves overpaid orders immediately and adds the excess to store credit (no hold). Bug: on a resubmitted order the old hold is never cleared, so it gets stuck On Hold, and no 'Payment confirmed' notification is sent. | System + paper | The paper says hold everywhere (REQ095, REQ098, Fig 2.6 text, Fig 2.11 text and diagram); approve-and-credit is what the client agreed to in the Interview 4 walkthrough. Fix the bug and reword the paper (C2). | High | S | p.59; Fig 2.11; Interview 4
REQ099 | Payment Verification | On Hold - Payment Not Received, reason, notify | Matches | js/admin-online-orders.js | 847c877: 'Payment not received' is its own hold type; customer sees 'Payment Rejected - Re-upload Needed'. (was: Exists only as a reason under 'Invalid payment', not as its own hold type.) | None | Use case text lists four hold types. | Low | S | p.59
REQ100 | Payment Verification | Auto-close after 7 days; verified payment kept as credit | Matches | js/orders.js:133 | Checked when a page loads (no background job). | None | Fine without a server. | Low | - | p.59
REQ101 | Payment Verification | Status to confirmed on approval | Matches | js/admin-online-orders.js:392 | - | None |  | Low | - | p.59
REQ102 | Payment Verification | Notify customer on verification | Matches | js/admin-online-orders.js:392 | Fixed: overpayment approval now notifies the customer. (was: Works for normal approvals; missing for overpayment approvals (see REQ098).) | None | Same fix as REQ098. | Med | S | p.59
REQ103 | Delivery | Compile name, address, contact, schedule, order ID; one-click copy | Matches | js/admin-online-orders.js:721 | 06574da: approved modal shows order no. and preferred schedule, with a Copy All button. (was: Separate copy buttons for address/name/contact/notes. Preferred schedule and order ID are not shown; no 'copy all'.) | None | Small; schedule is already saved on the order. | Low | S | p.59
REQ104 | Delivery | Mark Dispatched and enter Lalamove tracking URL | Matches | js/admin-online-orders.js:751 | Tracking link format is validated. | None |  | Low | - | p.59
REQ105 | Delivery | Reflect status to customer; customer 'Order Received' finalizes as Delivered | Deviates | js/order-details.js | Tracking link now shown to the customer. Remaining difference is wording: customer confirmation sets 'Received' after 'Delivered' (fix in paper). (was: Customer sees status, but not the tracking link. Customer confirmation sets 'Received' (a separate step after 'Delivered').) | System + paper | Show link (system); describe Delivered vs Received (paper) - see C1. | High | S | p.60
REQ106 | Delivery | Auto Dispatched -> Delivered after 3 days | Matches | js/orders.js:82 | - | None |  | Low | - | p.60
REQ107 | Delivery | Optional internal delivery notes | Matches | - | 06574da: optional internal delivery notes saved on dispatch. (was: Not built.) | None | Small. | Low | S | p.60
REQ108 | Live Chat Management | Staff view customer and AI conversations | Missing | admin/*.html 'Live Chat' href='#' | Sidebar link goes nowhere on all 12 admin pages. | Decision needed | Same decision as REQ035. | High | L | p.60
REQ109 | Live Chat Management | Staff respond to customers | Missing | - | Not built. | Decision needed | Same decision as REQ035. | High | L | p.60
REQ110 | Live Chat Management | Mark threads resolved | Missing | - | Not built. | Decision needed | Same decision as REQ035. | Med | S | p.60
REQ111 | Reports | Export daily sales reports (from Order Processing) | Partial | js/admin-online-orders.js (Export -> exportBlankPdf) | aece0e7: Online Orders Export now gives real PDF/Excel of the listed orders. Client's daily sales format still to build. (was: Online Orders Export downloads a blank PDF. Dashboard Sales Analytics export works but is not the daily sales report the client described (per customer, items with batch + expiry).) | Change system | Objective 3 and the client's one remaining ask in Interview 4 ('wala pa tayo dun sa reporting'). | High | L | p.60; Obj. 3; Interviews 2-4
REQ112 | Reports | Export monthly inventory + purchase reports (from Inventory) | Partial | js/admin-inventory.js (Export -> exportBlankPdf) | aece0e7: Inventory Export now gives real PDF/Excel by batch (expiry, supplier, receipt/DR no., unit cost, date received). Client's monthly format still to build. (was: Inventory Export downloads a blank PDF.) | Change system | Client needs batch, expiry, date received, receipt no., supplier (Interview 2, 4). | High | L | p.60; Interviews 2, 4
REQ113 | Reports | Pull-out reports by date range | Missing | - | Not built (write-offs are recorded, so data exists). | Change system | Client lists pull-out as a required monthly report (Interview 2). | High | M | p.60; Interview 2
REQ114 | Reports | Wholesale exchange reports by period | Missing | - | Not built; depends on REQ090. | Change system |  | Med | M | p.61
REQ115 | Reports | All reports in PDF or Excel | Partial | js/admin-dashboard.js:471 | aece0e7: all 6 Export buttons now give real PDF or Excel. Client report formats still to build. (was: Only Sales Analytics exports (PDF + Excel). Five other Export buttons give blank PDFs (Dashboard, Inventory, Online Orders, Suppliers, Audit Log).) | Change system |  | High | M | p.61
REQ116 | Customer Accounts | View profiles: status, registration date, order history | Matches | js/admin-customer-accounts.js:179 | 847c877: customer profile lists their orders with status. (was: Shows total order count, not the order list.) | None | Small. | Low | S | p.61
REQ117 | Customer Accounts | Deactivate without deleting | Matches | js/admin-customer-accounts.js:209 | - | None |  | Low | - | p.61
REQ118 | Staff Management | BM creates, modifies, revokes staff accounts | Matches | js/admin-staff-management.js:188 | 847c877: staff form uses the shared name/email/password rules; Administrator no longer demoted on edit. (was: Works (revoke = deactivate). New staff accounts skip the shared name/email/password validators, and editing an Administrator silently changes it to Branch Manager (js/admin-staff-management.js:181).) | None | Small. | Low | S | p.61
REQ119 | Staff Management | BM assigns roles that set accessible modules | Matches | js/admin-roles.js:14 | - | None |  | Low | - | p.61
REQ120 | Staff Management | Technical Staff cannot access Staff Management or Price Management | Matches | js/admin-roles.js:14 | Fixed with REQ071. (was: Staff Management is blocked. Price: see REQ071 (Technical Staff can set prices on new products).) | None | Fixed together with REQ071. | Med | S | p.61
REQ121 | Staff Management | Sales Staff: walk-in orders + catalog viewing only | Matches | js/admin-roles.js:14 | 57f4d80: Sales Staff limited to POS (with Today's Sales) + read-only catalog. (was: Sales Staff can also open Dashboard, Orders, Products (with editing), and Notifications. Orders access was added deliberately on 2026-10-01 for the Walk-in Orders tab.) | None | Client said Sales Staff is 'POS lang' (Interviews 2, 4). Either trim access, or reword REQ121 to include walk-in history. | Med | S | p.61; Interviews 2, 4
REQ122 | Audit Log | Log price changes, voids, wholesale exchanges, write-offs with user, time, record, before/after, reason | Partial | js/products-data.js:664 | Now also logs stock receiving, voids (reason), RX approvals/rejections, free-of-cost distributions and reconciliation variances with reason. Still free-text before/after; IP shown as '-'. (was: Logs price changes, write-offs, reconciliation, wholesale orders, account changes. Stock receiving is not logged (Fig 2.12 shows it). Voids and exchanges don't exist yet. Before/after values are free text, reasons mostly missing, IP shown as '-'.) | Change system | Comes with the void/exchange/reason work. | Med | M | p.61
REQ123 | Audit Log | Audit log accessible to BM and Technical Staff | Matches | js/admin-roles.js:14 | - | None |  | Low | - | p.62
REQ124 | Audit Log | Entries can't be edited or deleted | Matches | firestore.rules:156 | - | None |  | Low | - | p.62
REQNF001 | Usability | Consistent, organized layout | Matches | css/style.css | - | None |  | Low | - | p.62
REQNF002 | Usability | Meaningful feedback messages | Matches | js/products-data.js (showAppAlert) | - | None |  | Low | - | p.62
REQNF003 | Usability | Works on desktop, laptop, tablet, phone | Not verified | Bootstrap 5 responsive | Not yet tested on real phones/tablets. | Change system | Quick Playwright pass at phone widths. | Med | S | p.62
REQNF004 | Performance | Standard operations load in reasonable time | Not verified | - | Not measured. Several pages read whole collections. | None | Fine at client's volume (~50-100 customers/week, Interview 4). | Low | - | p.62
REQNF005 | Performance | Inventory/order changes appear without manual refresh | Deviates | all pages use one-time .get() reads | Users must reload to see new orders or stock changes. | Decision needed | Live listeners on key screens (verification queue, customer order page) are moderate work; or reword. | Med | M | p.63
REQNF006 | Performance | Reports in reasonable time | N/A | - | Reports not built yet. | None |  | Low | - | p.63
REQNF007 | Compatibility | Chrome, Firefox, Edge, Safari | Not verified | - | Not tested across browsers. | Change system | Test before defense. | Low | S | p.63
REQNF008 | Compatibility | Integrates OpenAI, EmailJS, QR PH | Partial | js/otp.js; js/emailjs-config.js | EmailJS works; QR PH is a static image (missing, see REQ028); OpenAI not integrated. | Decision needed | Follows the live chat decision. | Med | - | p.63
REQNF009 | Security | Passwords securely hashed, never exposed | Matches | Firebase Auth | Handled by Firebase Auth. | None |  | Low | - | p.63
REQNF010 | Security | Encrypted connection | Partial | start-server.bat (http-server) | Firebase calls are HTTPS, but the site itself is served over plain HTTP locally; no hosted deployment. | Decision needed | Resolved by deploying (see REQNF013). | Med | - | p.63
REQNF011 | Security | RBAC: customers can't reach admin; each staff role limited | Partial | js/admin-roles.js; firestore.rules:18 | Pages are restricted per role in the browser, but the database rules treat every staff role the same. | Change system | Tighten rules for prices, staff accounts, reconciliation. | Med | M | p.63
REQNF012 | Security | No patient data sent to OpenAI | N/A | - | No AI chat yet. | None | Applies only if chat is built. | Low | - | p.63
REQNF013 | Reliability | Hosted with uptime + recovery | Missing | - | Not hosted (Netlify blocked by billing); runs locally via http-server. | Decision needed | Firebase Hosting (free, HTTPS) is an option; otherwise move hosting to Limitations. | Med | S | p.64
REQNF014 | Reliability | Descriptive error messages | Matches | js/* | - | None |  | Low | - | p.64
REQNF015 | Scalability | Supports growth without structural change | Matches | Firestore | - | None |  | Low | - | p.64
REQNF016 | Scalability | New branches addable later | Matches | - | Single-branch by design (Limitations). | None |  | Low | - | p.64
REQNF017 | Maintainability | Modular code with documentation | Matches | js/* | 77336f3: README with setup, services, rules publishing, roles and deployment. (was: Modular, but no README or setup documentation (an error message even points to a missing README.md).) | None | Write a README. | Low | S | p.64
REQNF018 | Maintainability | Admins manage products/users/inventory without a developer | Matches | admin/* | - | None |  | Low | - | p.64
REQNF019 | Portability | Deployable elsewhere without restructuring | Matches | static site | - | None |  | Low | - | p.65
REQNF020 | Portability | Data export in PDF and Excel | Partial | js/admin-dashboard.js:471 | aece0e7: every Export button offers PDF or Excel. (was: Only Sales Analytics exports.) | Change system | Comes with the Reports module. | High | - | p.65
REQNF021 | Accessibility | Usable with basic digital literacy | Not verified | - | To be confirmed in the TAM evaluation. | None |  | Low | - | p.65
REQNF022 | Accessibility | Any modern browser, no install | Matches | - | - | None |  | Low | - | p.65
REQNF023 | Adaptability | New features without rebuild | Matches | - | - | None |  | Low | - | p.65
REQNF024 | Adaptability | Future courier/payment/SMS integration | Matches | - | - | None |  | Low | - | p.65
REQNF025 | Compliance | Data Privacy Act 2012 | Matches | footer links href='#' | Privacy Policy rewritten for the Data Privacy Act and linked from every footer (client to review). (was: Terms/Privacy shown at registration, but footer Privacy Policy and Terms links go nowhere.) | None | Point footer links to the existing legal text. | Med | S | p.65
REQNF026 | Cultural | English throughout | Matches | - | - | None |  | Low | - | p.66
REQNF027 | Cultural | Peso with 2 decimals and commas | Matches | js/products-data.js (formatPeso) | - | None |  | Low | - | p.66
REQNF028 | Cultural | Dates MM/DD/YYYY, 12-hour AM/PM | Matches | js/admin-inventory.js:210; js/admin-audit-log.js:63 | 847c877: one MM/DD/YYYY + 12-hour formatter on every screen, receipt and export. (was: Several screens use 'Oct 18, 2026' or 'October 2026'; the audit log uses a 2-digit hour.) | None | Small: one shared date formatter. | Low | S | p.66
REQNF029 | Cultural | Clear, professional language | Matches | shop/*.html footer | Filler text removed from the footer. (was: Footer says 'Amson about description sample text'.) | None | Copy fix. | Med | S | p.66

## Use Cases
Figure | Use case | Actor(s) | Status | Maps to | Notes
2.2 | Browse Product Catalog | Guest, Sales Staff | Matches | REQ009 | Sales Staff can browse the admin Products page.
2.2 | View Product Details | Guest | Matches | REQ013 | Dosage notes missing.
2.2 | Filter and Search Products | Guest | Matches | REQ010-012 | Header search + price/stock filters.
2.2 | Register Account | Guest | Matches | REQ001-006
2.2 | Access Live Chat | Guest | Missing | REQ035-037 | Dead buttons.
2.2 | Manage Live Chat | (no actor connected) | Missing | REQ108-110 | Paper: bubble has no actor line in the overall diagram.
2.2 | Process Walk-in Purchase | Sales Staff, Technical Staff | Matches | REQ082
2.2 | Login to Account | Sales, Technical, Registered User | Partial | REQ004-005, 043-045 | No unrecognized-device OTP.
2.2 | Update Account Settings | Sales, Technical, Registered User | Matches | REQ040-041 | No profile picture or email toggle.
2.2 | Manage Inventory | Technical Staff | Matches | REQ049-052
2.2 | Manage Online Order Queue | Technical Staff | Matches | REQ074-076
2.2 | Manage Product Catalog | Technical Staff | Matches | REQ068-070
2.2 | Manage Wholesale Accounts | Technical Staff | Matches | REQ085-086
2.2 | Process Wholesale Purchase | Technical Staff | Matches | REQ087
2.2 | Generate Reports | Technical Staff | Partial | REQ111-115 | aece0e7: exports are real PDF/Excel; client report formats still to build.
2.2 | Receive Supplier Delivery | Technical Staff | Matches | REQ062-063
2.2 | Month-End Stock Reconciliation | Technical Staff | Matches | REQ059-061 | 06574da: BM finalizes; variance reason logged.
2.2 | View Audit Log | Technical Staff | Matches | REQ123 | Overall diagram text implies BM-only - see C6.
2.2 | Update Product Price | Branch Manager | Matches | REQ071-073 | BM-only prices everywhere (publish rules).
2.2 | Create Staff Account | Branch Manager | Matches | REQ118
2.2 | Manage Staff Accounts | Branch Manager | Matches | REQ118-119
2.2 | View Order History | Registered User | Matches | REQ031-032
2.2 | Manage Cart | Registered User | Matches | REQ014-016 | 77336f3: cart saved on the account.
2.2 | Proceed to Checkout | Registered User | Matches | REQ017-020
2.2 | Process Prescription Pre Order | Registered User | Partial | REQ021-027 | 082ec92: approve/reject built. Name still differs from Fig 2.4 ('Submit Prescription Pre-Order') - paper edit.
2.3 | Access Live Chat | Guest | Missing | REQ035
2.3 | Browse Product Catalog | Guest | Matches | REQ009
2.3 | View Product Details | Guest | Matches | REQ013
2.3 | Filter and Search Products | Guest | Matches | REQ010-011 | Header search + price/stock filters.
2.3 | Register Account <<include>> Verify Email | Guest | Matches | REQ001-002
2.3 | Login to Account <<extend>> Verify OTP | Staff, Registered User | Missing | REQ005, REQ044 | Verify OTP not built.
2.3 | Login to Account <<extend>> Recover Password | Staff, Registered User | Matches | REQ007, REQ046
2.3 | Update Account Settings | Staff, Registered User | Matches | REQ040-042
2.4 | Submit Prescription Pre-Order | Registered User | Matches | REQ021-027 | 082ec92: separate prescription approval/rejection with reason.
2.4 | Add Item to Cart | Registered User | Matches | REQ014
2.4 | View Order History | Registered User | Matches | REQ031
2.4 | <<extend>> Download Order Receipt | Registered User | Matches | REQ033
2.4 | <<extend>> Track Order Status | Registered User | Matches | REQ034 | Tracking link shown once dispatched.
2.4 | <<extend>> Confirm Order Receipt | Registered User | Matches | REQ105 | Sets 'Received' - see C1.
2.4 | Manage Cart | Registered User | Matches | REQ015-016
2.4 | Proceed to Checkout <<include>> Upload Payment Proof <<include>> Place Order | Registered User | Matches | REQ017-030 | Paper: include chain direction is unusual (Upload Payment Proof including Place Order).
2.5 | Manage Inventory | Technical Staff (+BM) | Matches | REQ049
2.5 | <<extend>> Monitor FEFO Expiration Alerts | Technical Staff (+BM) | Partial | REQ065-067 | 6-month flag yes; 2-month Bad Order missing.
2.5 | <<extend>> Write Off Unsellable Stock <<include>> Record Reason | Technical Staff (+BM) | Matches | REQ051-052
2.5 | Month-End Stock Reconciliation <<include>> Enter Physical Counts | Technical Staff (+BM) | Matches | REQ059-061 | 06574da: BM finalizes; variance reason logged.
2.5 | Receive Supplier Delivery <<include>> Add Stock Receiving Entry | Technical Staff (+BM) | Matches | REQ062-063
2.5 | Create Purchase Order | Technical Staff (+BM) | Matches | REQ053 | Paper: missing from overall diagram 2.2.
2.6 | Process Walk-in Purchase | Sales Staff, Technical Staff | Matches | REQ082
2.6 | <<include>> Generate Transaction Record | Sales/Technical | Matches | REQ092 | Retail only; no wholesale invoice.
2.6 | <<extend>> Print Transaction Receipt | Sales/Technical | Matches | Modules p.44 | 57f4d80: Print button with 58mm receipt layout.
2.6 | <<extend>> Void Walk-in Transaction <<include>> Record Reason for Void | Technical Staff (+BM) | Matches | REQ083 | 57f4d80: void with required reason.
2.6 | Manage Online Order Queue <<extend>> Verify Proof of Payment | Technical Staff (+BM) | Matches | REQ094-095
2.6 | <<extend>> Place Order on Hold | Technical Staff (+BM) | Matches | REQ096-099
2.6 | <<extend>> Confirm Online Order <<include>> Generate Transaction Record | Technical Staff (+BM) | Matches | REQ101
2.6 | Generate Reports <<extend>> Export Reports | Technical Staff (+BM) | Partial | REQ111-115 | aece0e7: exports are real PDF/Excel; client report formats still to build.
2.6 | Process Wholesale Purchase <<include>> Record Wholesale Purchase Order | Technical Staff (+BM) | Matches | REQ087 | No wholesale sales invoice.
2.6 | (no bubble) Verify Prescription | - | N/A | REQ077-081 | Paper: RX verification has requirements but no use case in Fig 2.2 or 2.6.
2.6 | (no bubble) Free-of-Cost Distribution | - | N/A | REQ091 | Paper: no use case in any figure (wholesale exchange is in Fig 2.7).
2.7 | Manage Live Chat | Technical Staff (+BM) | Missing | REQ108-110 | Connected here, but not in Fig 2.2.
2.7 | Manage Product Catalog | Technical Staff (+BM) | Matches | REQ068-070 | Dosage notes missing; category rename uses native prompt.
2.7 | Manage Supplier Accounts | Technical Staff (+BM) | Matches | REQ069
2.7 | Manage Wholesale Accounts | Technical Staff (+BM) | Matches | REQ085-086 | No document expiry tracking.
2.7 | <<extend>> Process Wholesale Exchange Request | Technical Staff (+BM) | Missing | REQ090
2.7 | <<include>> Adjust Inventory for Exchange | Technical Staff (+BM) | Missing | REQ090
2.7 | Manage Online Customer Accounts | Technical Staff (+BM) | Matches | REQ116-117 | 847c877: order history listed in the profile.
2.7 | View Audit Log | Technical Staff (+BM) | Matches | REQ123-124
2.7 | Update Product Price | Branch Manager | Matches | REQ071-072 | BM-only prices everywhere (publish rules).
2.7 | <<include>> Record Price Change in Audit Log | Branch Manager | Matches | REQ073 | No reason captured.
2.7 | Create Staff Account <<include>> Assign Staff Role | Branch Manager | Matches | REQ118-119 | Shared validators not applied.
2.7 | Manage Staff Accounts | Branch Manager | Matches | REQ118 | Editing an Administrator silently changes it to Branch Manager.

## Activity Diagrams
Figure | Step / flow | Paper shows | System does | Status | Recommendation | Notes
2.8 | Validate credentials -> role redirect | Valid login: customer to Home, staff to Dashboard | Same (js/auth.js:94) | Matches | None
2.8 | Failed attempts | Increment count; at 5, lock 2 minutes; back to Login page | Same (js/auth.js:57) | Matches | None
2.8 | Device recognition + OTP | Check if device is recognized; if not, send and validate OTP | Not built | Missing | Change system | REQ005/REQ044.
2.8 | Wrong OTP | Diagram: 'No' from Validate OTP joins the failed-attempt counter (counts toward lockout). Text p.77: user is prompted to request a new OTP. | - | N/A | Change paper | Diagram and text disagree (C13).
2.8 | Steps the system has that the diagram lacks | Not shown | reCAPTCHA check, rejecting attempts while locked, blocking deactivated accounts, sending unverified customers to email verification | Deviates | Change paper | Add to diagram; all are in requirements (REQ003, REQ004, REQ117, REQ002).
2.9 | Validate fields -> duplicate email -> Terms -> send code | Fields validated, then duplicate check, then Terms shown and accepted, then code sent | Terms modal opens when the checkbox is ticked (before submit); duplicate email is caught by Firebase at account creation; code sent after | Deviates | Change paper | Same outcome, different order (C14).
2.9 | Wrong / expired code | Loop back to Enter Code (diagram); text p.79 adds 'request a new code' | Retry or Resend link (js/verify-email.js) | Matches | Change paper | Add Resend to diagram.
2.9 | After verification | Go to Login | Goes straight to the shop, already signed in | Deviates | Change paper | C10.
2.9 | Account activation | Account activated only after the code is verified | Login account is created first with emailVerified:false; unverified customers are redirected to verification on login | Partial | None | Functionally equivalent; note the REQ002 bypass issue.
2.10 | Catalog -> cart -> checkout | Browse, add to cart, updated cart summary, checkout | Same, plus choosing which cart items to check out | Matches | None | Cart selection is an addition.
2.10 | Default address | If saved, pre-fill; else enter | Same (js/checkout.js) | Matches | None
2.10 | RX check position | Diagram: RX is checked after the address and after uploading payment proof, so RX customers are still asked for a delivery address. Text p.81: RX check comes before payment and delivery is not allowed. | RX detected when checkout opens; address section hidden; pick-up only | Deviates | Change paper | Diagram contradicts REQ023 and its own text (C15).
2.10 | Prescription photo upload | Not shown in the diagram (text p.81 and REQ021 require it) | Required on the payment page for RX orders | Deviates | Change paper | C15.
2.10 | Order status after submission | Recorded as Pending Payment Verification (RX included) | Same ('placed' = Order Pending Verification) | Matches | None | Diagram supports the system; REQ024 says 'Pending Prescription Verification' (C3).
2.10 | Order submission notification | System sends a notification to the customer | Only an on-screen confirmation with the order number; no notification | Missing | Change system | Small: add an order-placed entry to the customer bell.
2.10 | Steps the system has that the diagram lacks | Not shown | Login required to check out, delivery schedule, store credit discount, live stock re-check before submitting | Deviates | Change paper | Optional: add to diagram (delivery schedule is in Modules p.39).
2.11 | Valid payment | Confirm -> notify customer -> FEFO stock deduction -> receipt | Stock is deducted first; if stock ran out the order goes on an Out of Stock hold instead | Deviates | Change paper | Diagram has no out-of-stock path (C19).
2.11 | RX pre-order after confirmation | Diagram: admin copies delivery details, books courier and provides a tracking link before the system checks for RX | RX orders skip courier booking and go straight to Ready for Pick-up | Deviates | Change paper | RX orders can't be delivered (REQ080) (C17).
2.11 | Prescription review | Not shown (payment screenshot only) | 082ec92: approve or reject (reason) before preparation; notify customer | Matches | None | REQ077-079 require it (C3).
2.11 | Dispatch | Admin provides tracking link; system marks Dispatched | Customer now sees the tracking link; marking Dispatched with the link is still one step | Partial | Change system | REQ034.
2.11 | Invalid payment | On Hold -> record reason -> notify customer -> re-upload -> back to admin review | Same (js/admin-online-orders.js:561; js/order-details.js) | Matches | None
2.11 | Resolution without re-upload | Diagram: if the customer 'performed resolution action', the system confirms the order with no admin review | Every resolution returns to staff (resubmission or Release Hold) | Deviates | Change paper | Diagram contradicts REQ101 (C18).
2.11 | Overpayment | Treated as an invalid payment (hold) | Approved immediately; excess added to store credit | Deviates | Change paper | C2.
2.11 | Expired hold | Admin marks the order Unresolved | Closed automatically after 7 days, with verified payment kept as credit | Deviates | Change paper | REQ100 says automatic; move step to System lane and add credit retention.
2.11 | Steps the system has that the diagram lacks | Not shown | Fully credit-covered orders (no screenshot), Release Hold by staff | Deviates | None | Optional to add.
2.12 | Write-off | Select product + qty, reason -> deduct -> audit log -> low-stock check/alert | Same (js/admin-inventory.js:994) | Matches | None
2.12 | Stock receiving with a PO | Link PO -> enter details -> match? add stock -> audit log -> low-stock check | Receiving is now written to the audit log | Matches | None | REQ122.
2.12 | Stock receiving: PO mismatch | Diagram box repeats 'Verify if received quantities match PO quantities' -> partial stock added -> end | Partial stock added, PO marked Discrepancy, acknowledgment required to close | Deviates | Change paper | Copy-paste error in the diagram; should be 'Generate Discrepancy Report / Mark PO as Discrepancy', plus the acknowledgment step.
2.12 | Stock receiving without a PO / batch upload | Not shown (text p.85 describes both) | Both exist (manual Receive Stock, Excel/CSV upload) | Deviates | Change paper | Add the no-PO branch and batch upload to the diagram.
2.12 | 6-month flag | Flag for pull-out -> expiration alert -> admin chooses Write Off or Reserve for Free-of-Cost | Flagged automatically as Wholesale Only (only when Inventory opens) + alert; no pull-out action choice | Partial | Change system | REQ066 timing fix; 'Reserve for free-of-cost' could just be the Wholesale Only flag + REQ091.
2.12 | 2-month Bad Order | Flag Bad Order -> alert -> 'Apply FEFO-Based Stock Deduction' | Not built | Missing | System + paper | Build REQ067; diagram should say 'Write off / deduct the batch', not FEFO deduction.
2.12 | Expiry decision order | Diagram tests '<6 months' before '<2 months' (every <2-month batch also matches <6) | - | N/A | Change paper | Test <2 months first.
2.13 | Find or create buyer account | Search -> if new, enter details, upload documents, save | Accounts searchable; create with LTO/permit upload (js/admin-wholesale-accounts.js:270) | Matches | None
2.13 | Check documents are current | Text p.87: verify documents, upload renewals if expired. Diagram: 'View Buyer Documents' only | 5cad255: LTO/permit valid-until dates; expired documents block the order | Matches | None | REQ086 expiry dates; add the validity check to the diagram.
2.13 | Purchase history | View purchase history | 5cad255: Purchase History per buyer | Matches | None | REQ089.
2.13 | Near-expiry items | Enable free-of-cost pricing option for near-expiry items | 5cad255: free-of-cost option with reason and audit entry | Matches | None | REQ091.
2.13 | Confirm -> FEFO -> sales invoice | Confirm, FEFO deduction, generate sales invoice | 5cad255: sales invoice PDF with buyer, batch and expiry | Matches | None | REQ092.
2.14 | Select products, confirm, FEFO | Select products + qty -> confirm -> FEFO deduction | Same, plus a review screen with Edit/Confirm, payment method and change | Matches | Change paper | Optionally add the review step and payment method to the diagram.
2.14 | RX item | Physically verify prescription -> 'Mark RX as Verified' (drawn in the System lane) | 57f4d80: RX Verified checkbox + notes in POS | Matches | None | Build REQ084. In the diagram, marking verified is a staff action, so it belongs in the staff lane.
2.14 | Print receipt | System prints receipt | 57f4d80: Print button, 58mm layout | Matches | None
2.14 | Void | Not shown (text p.89 and Fig 2.6 include it) | 57f4d80: void built | Partial | Change paper | Add the void branch to the diagram.
2.15 | Select buyer -> order -> returned item -> replacement -> reason | As listed | Not built | Missing | Change system | REQ090.
2.15 | Inventory adjustment | Diagram: FEFO deduction of the replacement only. Text p.91: returned item also added back to stock | Not built | Missing | System + paper | Add 'Return item to stock' to the diagram.
2.15 | Audit log + document | Diagram: 'Generate Sales Invoice'. Text p.91: audit log entry + 'wholesale exchange document' | Not built | Missing | System + paper | Add the audit step and use one document name; REQ114 reports on these.
2.15 | Lane placement | 'Display Buyer Account and Order History' drawn in the Admin lane | - | N/A | Change paper | Move to the System lane.

## Contradictions
ID | Topic | Where the paper (or client) disagrees | What the system does | Recommendation
C1 | Who sets 'Delivered', and is there a 'Received' step? | REQ031 (no Received), REQ105 (customer confirmation finalizes Delivered), REQ106 (auto Delivered after 3 days), Modules p.39-40 (customer marks delivered), Interview 4 ('mark as delivered siya ni customer') | Staff marks Delivered or it auto-advances after 3 days; customer then confirms 'Received'. | Change paper: define Delivered (staff/auto) and Received (customer) in REQ031, REQ105, Fig 2.4 text.
C2 | Overpayment: hold or approve? | REQ095, REQ098, Fig 2.6 text and Fig 2.11 text + diagram all treat overpayment as a hold (excess recorded as unapplied value) vs Interview 4 walkthrough (enter the excess; it goes to the customer's account for the next order; client agreed) | Approves immediately and credits the excess. | Change paper: rewrite REQ098 and Fig 2.6/2.11 to approve-and-credit; drop overpayment from the hold types.
C3 | Is prescription approval a separate step? | REQ024, REQ077-079, Modules p.43, Conceptual Framework, Fig 2.10 text (dedicated RX queue, 'Pending Prescription Verification', approve/reject with reason) vs Fig 2.10 diagram (RX recorded as Pending Payment Verification) and Fig 2.11 text + diagram (RX confirmed like any order, verification in person) | Same as Fig 2.10/2.11 diagrams (payment approval only). | Change system to match REQ077-079; then fix Fig 2.10 and 2.11.
C4 | When can a walk-in sale be voided? | REQ083 ('before finalization') and Fig 2.6 text ('void a completed transaction before finalization') vs Modules p.43 ('completed transactions may be voided', with original receipt number) vs Interview 4 (void after the receipt is printed, with receipt number, reason, optional exchange; not by a junior staff member alone) | No void. | Build void for completed sales with original receipt number; reword REQ083 and Fig 2.6/2.14 text to 'completed'.
C5 | Who does month-end reconciliation? | REQ061 (Branch Manager finalizes) vs Modules p.42 ('authorized staff' submit) vs Fig 2.5 text ('Branch Manager may open') vs Fig 2.5 diagram (Technical Staff connected) | Anyone with Inventory access opens and finalizes. | Technical Staff counts, Branch Manager finalizes. Align REQ061, Fig 2.5 text, and system.
C6 | Who can view the audit log? | Fig 2.2 text ('Branch Manager ... in addition to ... audit log review', implying BM-only) vs REQ123 and Fig 2.2 diagram (Technical Staff - View Audit Log) | BM and Technical Staff. | Change paper: fix the Fig 2.2 description sentence.
C7 | Near-expiry rules | REQ066 (6 months: remove + free-of-cost wholesale), REQ067 (2 months: Bad Order + auto-deduct), Modules FEFO p.41 (6-month pull-out only), Conceptual Framework (6-month pull-out, 2-month disposal), Interview 1 (6 months pull-out, 2 months BO) | 6-month wholesale-only flag; no 2-month handling. | Build 2-month Bad Order; add it to the Modules FEFO paragraph.
C8 | Price change reason | REQ073 (previous price, new price, timestamp) vs REQ122 (reason for each entry) vs Interview 2 (client requires reason and date) | No reason captured. | System + paper: add a reason field; add 'reason' to REQ073.
C9 | Wholesale 'agreed pricing' | REQ085/087 (per-account agreed pricing) vs Interview 2 (special price for wholesalers, retail price online) | Product-level wholesale price, editable per order. | Change paper: describe a default wholesale price per product, adjustable per order.
C10 | Email verification destination | Fig 2.9 text + diagram (after verification, go to Login) | Redirects straight to the shop (already signed in). | Change paper (minor).
C11 | Overall diagram completeness | Fig 2.2 has no Create Purchase Order, Batch Upload, Verify Prescription, Payment Verification, Delivery, Customer Accounts, Suppliers, Notifications, Wholesale Exchange (all appear in Figs 2.5-2.7); 'Manage Live Chat' has no actor in 2.2 but is linked to Technical Staff in 2.7 | - | Change paper: add the missing bubbles to 2.2 or say it's a summary; connect Manage Live Chat.
C12 | Pre-order naming | Fig 2.2 'Process Prescription Pre Order' vs Fig 2.4 'Submit Prescription Pre-Order' | - | Change paper: use one name.
C13 | Wrong OTP at login | Fig 2.8 diagram (wrong OTP feeds the failed-attempt counter) vs Fig 2.8 text p.77 (prompted to request a new OTP) | No OTP yet. | Pick one when building REQ005/044; update the other.
C14 | Registration order | Fig 2.9 (validate, duplicate check, then Terms) vs system (Terms when ticking the checkbox, duplicate check at account creation) | See left. | Change paper: Terms before submit; duplicate check after.
C15 | RX in the purchasing flow | Fig 2.10 diagram (RX checked after address and payment upload; no prescription upload) vs Fig 2.10 text p.81 and REQ021/023 (RX decided first, pick-up only, prescription photo required) | Matches the text, not the diagram. | Change paper: redraw the RX branch in Fig 2.10.
C16 | Order submission notification | Fig 2.10 (system notifies customer on submission) vs REQ039 (order confirmations) | No notification on submission. | Change system (small).
C17 | RX pre-orders and couriers | Fig 2.11 diagram (courier booked and tracking link sent before the RX check) vs REQ023/080 (never delivered) | RX skips courier booking. | Change paper: branch RX before the courier steps.
C18 | Resolving a hold | Fig 2.11 diagram (customer resolution without re-upload confirms the order automatically) vs REQ101 (admin approval confirms) | Every resolution goes back to staff. | Change paper.
C19 | Stock check at confirmation | Fig 2.11 (notify confirmed, then FEFO deduction; no shortage path) vs REQ050 | Deducts first; shortage puts the order on an Out of Stock hold. | Change paper: add the out-of-stock hold branch.

## Tech Stack
Area | Paper says | System uses | Recommendation | Notes
Image/file storage | Google Firebase cloud storage (pp.35-36) | Cloudinary (js/cloudinary.js) | Change paper | Firebase Storage needs the Blaze plan; Cloudinary is free. Name it in Technical Background and Software list.
Hosting | Netlify (pp.35, 37, Budget) | Netlify (set up); local http-server for testing | None | DECIDED: stay on Netlify. Budget row must match the chosen plan; Netlify Functions host the OpenAI call.
Tables | DataTable (pp.35, 37) | Custom tables with search/sort/pagination | Change paper | Remove DataTable or describe as custom-built.
Searchable dropdowns | Not mentioned | Choices.js | Change paper | Add to Software list.
Email | EmailJS for OTP, order confirmations, password reset (p.36) | EmailJS for OTP only; password reset by Firebase Auth; no order emails | System + paper | Order emails are REQ039 (system). Password reset wording is paper.
AI chat | OpenAI API (pp.35, 37) | Not integrated yet | Change system | DECIDED: Gemini via Firebase AI Logic (free tier, no server needed); Groq as fallback. In the panel letter.
Receipt printing | Thermal receipt printing (pp.33, 44, 89) | No print | Change system | Browser print with a 58mm print stylesheet covers it.
Payment | QR PH static QR + screenshot | QR PH image file missing from repo | Change system | Add the client's QR image.
Charts / PDF / Excel | Chart.js, jsPDF, SheetJS | Same | None
Database wording | 'Real-time database' (p.35-36) | Cloud Firestore (one-time reads, not live listeners) | Change paper | Name the product correctly; see REQNF005 on live updates.
Icons / fonts | Not mentioned | Bootstrap Icons, Google Fonts (Roboto) | Change paper | Add to Software list.
Version control / CI | Netlify continuous integration with the repo | GitHub repo (phobiaax/Amson, branch webapp); no CI/deploy | Change paper | Add Git/GitHub; CI depends on hosting decision.
Local serving | Not mentioned | Node.js http-server via start-server.bat | Change paper | Mention for the demo setup.
Mockup tool | Canva (p.38) vs 'Creation of Figma' (Gantt p.97) | - | Change paper | Use one name.
Dashboard analytics | Chart.js for sales and inventory movement | Sales charts only; inventory as count tiles | Change paper | Reword or add an inventory chart.
CAPTCHA | Google reCAPTCHA | Same | None
Auth / database | Firebase Auth + Firestore | Same | None

## Paper Edits
Where in the manuscript | Change
REQ007 / Technical Background p.35-36 | Password reset link is sent by Firebase Authentication, not EmailJS.
REQ008 p.47; Modules p.38 | Drop 'promotions' unless you plan them; keep 'announcements' (banner to be built).
REQ031 p.50 | Replace status list with: Pending Verification, Payment Confirmed, Dispatched / Ready for Pick-up, Delivered, Received / Picked Up, On Hold (with type), Closed (Unresolved).
REQ073 p.55 | Add 'and the stated reason' (client requirement, Interview 2) - after the reason field is built.
REQ083 p.56; Fig 2.6 text p.73; Fig 2.14 text p.89 | Void applies to completed transactions, referencing the original receipt number (C4).
REQ085, REQ087 p.57; Modules p.44 | Default wholesale price per product, adjustable per order (C9).
REQ095, REQ098 p.58-59; Fig 2.6 text p.74; Fig 2.11 text p.83 | Overpayment is approved and the excess is added to the customer's store credit; three hold types plus overpayment-approval (C2).
REQ105 p.60; Fig 2.4 text p.71; Modules p.39-40 | Delivered is set by staff (or automatically after 3 days); the customer's confirmation marks it Received (C1).
REQ121 p.61 | Only if you keep Sales Staff access to Walk-in Orders history: add it to REQ121.
Fig 2.2 text p.67 | Audit log is available to Technical Staff and Branch Manager (C6).
Fig 2.2 diagram | Connect 'Manage Live Chat' to Technical Staff; add missing bubbles or label as summary (C11); one name for the pre-order use case (C12).
Fig 2.5 text p.72 | Technical Staff opens/counts; Branch Manager finalizes (C5).
Fig 2.2 / 2.7 diagrams | Overpayment, free-of-cost distribution: no bubble anywhere; add 'Record Free-of-Cost Distribution' under Manage Wholesale Accounts if REQ091 stays.
Fig 2.8 diagram + text p.76-77 | Add reCAPTCHA, locked-account check, deactivated-account check, unverified-email redirect; make the wrong-OTP path match the text (C13).
Fig 2.9 diagram + text p.78-79 | Terms accepted before submit, duplicate email caught at account creation (C14); add Resend Code; end at the shop, signed in (C10).
Fig 2.10 diagram | Move the RX decision to the start of checkout; RX skips the address; add Upload Prescription Photo (C15); optionally add delivery schedule and store credit.
Fig 2.11 diagram + text p.82-83 | Prescription approval/rejection before confirmation (C3, after it is built); RX skips courier steps (C17); resolved holds return to admin review (C18); stock shortage -> Out of Stock hold (C19); overpayment approved with credit (C2); expired holds closed by the System lane, credit kept.
Modules FEFO p.41 | Add the 2-month Bad Order step (C7).
Technical Background p.35-37; Budget p.99 | Cloudinary instead of Firebase Storage; Choices.js added; DataTable removed; hosting per decision (Tech Stack sheet).
Scope p.6; Product Browsing REQ009 | The client also sells medical supplies and grocery items (monthly report); the paper only mentions OTC/prescription medicines. Mention them, or exclude them on purpose.
Scope and Limitations p.7 | Add: system receipts/invoices are internal records, not BIR-registered official receipts; BIR/VAT receipts stay manual on request; no BIR or government integration (client policy, Interview 1).
Decision-dependent | Live chat/AI (Obj. 1, Scope, Framework, REQ035-038, REQ108-110, NF008, NF012); real-time refresh (NF005); hosting (NF013); wholesale price visibility (REQ088).

## Removals (Letter)
Change | Paper location | What gets removed / narrowed | How to avoid the letter | Recommendation
Promotions on the home page | REQ008 p.47; Modules p.38 | 'promotions' dropped | Build a simple promotions/announcements banner (same component as the store-closure banner) | Building - no letter (S)
'Payment Rejected' order status | REQ031 p.50 | Status list replaced; 'Payment Rejected' no longer exists | Show invalid-payment holds to the customer as 'Payment Rejected - re-upload needed' | Building - no letter (S)
Per-account agreed wholesale pricing | REQ085, REQ087 p.57; Modules p.44 | Agreed price per buyer replaced by one wholesale price per product | Add an optional agreed price per buyer per product, used as the default on their orders | Building - no letter (M)
'On Hold - Overpayment' | REQ095, REQ098 p.58-59; Fig 2.6, 2.11 | Overpayment hold type removed (system approves and credits instead) | Ask the adviser whether this is a refinement (excess still kept as unapplied value, as REQ098 requires). Otherwise change the system to hold overpaid orders until staff apply the excess | In letter (as a refinement the client approved)
Real-time updates everywhere | REQNF005 p.63 | Limited to the verification queue and customer order page | Use live updates on all order and inventory screens | Building - no letter (M)
Wholesale prices admin-only | REQ088 p.57 | Moved to Limitations (prices are hidden on screen but readable in the database) | Move costing/wholesale prices to a staff-only collection | Building - no letter (M)
Push notifications | Theoretical Framework p.23 | 'Instantaneous push notifications' reworded to in-app alerts | Add browser notifications for staff alerts | Building - no letter (S)
Chart.js inventory analytics | Technical Background p.35-37 | Inventory movement charts not provided | Add an inventory movement chart to the dashboard | Building - no letter (S)
Price locking | Modules p.42 | 'Allows price locking' reworded | Add a lock/unlock toggle per product for the Branch Manager | Building - no letter (S)
OpenAI API | 9 places: pp.3, 4, 24, 26, 34, 35, 37-38, 63 | Replaced by a free provider (Gemini via Firebase AI Logic, if approved) | Keep OpenAI (paid, prepaid credit) | In letter (same letter as the other tool swaps)
DataTable library | Technical Background p.35, 37 | Removed (custom tables used) | Use the DataTables library on the main tables | In letter
Firebase Storage for images | Technical Background p.35-36 | Replaced by Cloudinary | Move uploads to Firebase Storage (needs the paid Blaze plan) | In letter
EmailJS for password reset | Technical Background p.36 | Replaced by Firebase Auth's own reset email | Send reset links through EmailJS | In letter
Who the system serves | Scope p.6; Conceptual Framework p.25 | 'Wholesale clients' and 'main office' as users; wholesale buyers registering/ordering online | None - the original text is inaccurate (wholesale is staff-recorded per the client) | In letter (correction)

## Report Formats
Client report | Section / columns | System data today | Gap | To-Do
Daily Sales (PDF) | Header: store name, date range 12:00:01 AM - 11:59:59 PM | - | - | Reports module
Daily Sales (PDF) | Sales: Date, No. of Orders, Total, Discount/Deduction, Grand Total, Less VAT, VATable Sales, VAT 12%, VAT Exempt Sales | posSales, orders, wholesaleOrders totals | No discounts; no VAT fields (sample day: all VAT-exempt) | Discount decision; VAT question to client
Daily Sales (PDF) | Pay-In, Pay-Out, TOTAL | - | Not recorded | Pay-in/pay-out decision
Daily Sales (PDF) | Retail Sales: Date, No. of Items, Total Amount | posSales + online orders | OK once combined
Daily Sales (PDF) | Wholesale Sales: Date, No. of Items, Total Amount | wholesaleOrders | OK
Daily Sales (PDF) | Payment Method: Bank Transfer, Cash, Credit, G-Cash, Terminal - orders + amount | posSales.paymentMethod (cash/card/e-wallet only) | No Bank Transfer/Credit; wholesale has no payment method | Payment method + terms item
Daily Sales (PDF) | Item Sold: Item, No. of Items, Total Amount, Discount (sorted by qty) | sale line items | OK (no discount)
Customer File (Excel, daily) | Customer Name, Date+time, SI#, Batch No, Exp, Qty, Item, Sales Price, Total Amount, Terms of Payment; subtotal per customer | sale line items | No batch/expiry per line, no SI#, no walk-in customer name, no terms | Batch per sale; SI#; walk-in name; payment terms
Monthly Inventory (Excel) | One sheet per category (Generics, Medical Supplies, Grocery, Drugstore per pc, Branded): Product, POS stock, Physical count, Costing, Retail, Wholesale, Batch #, Expiry | stockBatches + reconciliation counts + product prices | Categories differ; needs reconciliation export by category | Categories item; Reports module
Monthly Return to POS (Excel) | Item, Batch, Expiry, Customer, DR#, Date Purchased, Date Returned, Qty, Amount, Total | - | Wholesale exchange/return not built; no DR#/SI# on the original sale | Wholesale exchange; SI#
Monthly Supplier Purchases (Excel) | Supplier Name, Order Date, Receipt #, Product, Brand, Packs, Batch #, Expiry, Qty, Price, Amount, Total; separate Drugstore and Grocery sheets | stockBatches (supplier, batch, expiry, qty, date) | No receipt #, unit cost, pack on receiving | Receiving fields item
Observations | Their old POS shows negative stock (-1); several expiries are typed into product names (e.g. '4/28'); one batch cell can list several expiries | - | Our system blocks negative stock and keeps one expiry per batch - good defense talking points; data needs cleaning before import | Catalog import item

## Interview Asks
Interview | What the client asked | Where it's covered | Status
1 | Price lock: one person changes prices, can lower then restore, changes monitored | To-Do: price lock item; REQ071-073 | Covered
1, 4 | Void / cancel with lock, reason, receipt number, stock restore, exchange | To-Do: walk-in void; receipt numbers | Covered (rules added from Interview 4)
1 | Reports with batch + expiry, summarized, copy-paste into office Excel | To-Do: Reports module | Covered
1 | 'Keep' a punched walk-in order until the customer confirms | To-Do: park/hold sale | Added now (Decision)
1 | Small thermal receipt printer | To-Do: receipt printing | Covered
1 | Usable on the manager's phone | REQNF003 test pass | Covered
1 | Not connected to BIR or government; confidential | To-Do: 'not an official receipt' relabel; Limitations edit | Added now
1 | Announce closure days to buyers | To-Do: announcement banner (REQ008) | Added now
1 | Free goods: near-expiry RX only to doctors, vitamins to all | To-Do: wholesale free-of-cost (note) | Added now (note)
1 | Multi-branch / Manila branch use | Limitations p.7 (single branch) | Out of scope
2 | Sales Staff = POS only | REQ121 decision | Covered
2 | Wholesale not online; retail price only online | REQ088 (wholesale price visibility) | Covered
2 | Wholesale documents: LTO + business permit, latest copies | REQ086 expiry tracking | Covered
2 | POS receipt printed; BIR receipt with VAT only on request | 'Not an official receipt' item; Limitations edit | Added now
2 | Send the sales invoice format | Client item | Covered
2 | Price change needs reason and date (option or free note, e.g. 'approved by boss') | Price lock item | Covered
2 | Customer file per wholesale buyer; reorder past purchases | Wholesale history item (reorder added) | Added now (reorder)
2 | Daily sales (per customer, items, batch, expiry); monthly purchases (batch, expiry, purchase date, receipt no., supplier); monthly inventory; pull-out; returns | Reports module; supplier DR number field | Added now (DR number)
2 | Wholesale returns as item exchange, no money back | Wholesale exchange item | Covered
2 | Free-of-cost for wholesale only | Wholesale free-of-cost item | Covered
2, 3 | Lalamove only; payment first, no COD; customer pays rider | REQ020; Terms rewrite | Covered
2, 3 | Rider details recorded | Delivery notes item (note) | Added now (note)
2 | Daily cash remitted to main office | Reports module (totals by payment method) | Added now (note)
3 | Live chat on the website | Live chat decision | Covered
3, 4 | No third-party payment; QR Ph direct, verified on the spot | REQ028 QR image | Covered
3 | Wrong item delivered: exchange, no refund; no cancellation after payment; failed-delivery fees on customer | Terms rewrite | Added now
4 | Report export must look like the client's sample | Client item; Reports module | Covered
4 | Export the dashboard | Reports module (Dashboard Export button) | Covered
4 | See history of what came from each supplier | Supplier history item | Added now
4 | See wholesale permit expiry | REQ086 | Covered
4 | Audit log shows who added stock/products | REQ122 completeness | Covered
4 | Void restricted: a second person must see it | Walk-in void item (note) | Added now (note)
4 | Hands-on before go-live | User manual + training item | Added now

## Manuscript Pass
Section | Page | Item | Area | Defense risk | Effort
Title page / cover | i | Still labelled 'Capstone Project Proposal' dated May 16, 2026; update the label and date for the final manuscript. | Paper | Med | S
Title | i | 'Integrated Real-Time Expiry Monitoring': near-expiry stock is only flagged when the Inventory page opens (REQ066). Fix the system so the title holds (To-Do: REQ066 item). | System | High | -
Whole paper | - | About 100 'will ...' sentences are written as a proposal. Ask the adviser whether the final manuscript should switch to past/present tense, then convert. | Paper | Med | M
Whole paper | - | Spelling consistency: 'Fulfilment' on the cover vs 'fulfillment' elsewhere. | Paper | Low | S
Whole paper + system | - | 'QR PH' in the paper and most screens, 'QR Ph' on the payment page image text. The official name is 'QR Ph'; pick one everywhere. | Both | Low | S
Project Context | p.1 | Says the old POS couldn't print batch numbers, expiration dates or supplier details on receipts. The new receipts don't show them either; add batch/expiry to receipts and reports, or soften the sentence. | System | Med | S
Project Context / Purpose | p.2-4 | AI chat 'addresses inquiries at any hour': depends on the live chat decision. | Decision | High | -
Purpose and Description | p.3 | 'Each completed transaction ... made available for printing and reporting': needs receipt printing and the Reports module. | System | High | -
Objectives | p.5 | Obj. 1 promises AI chat support (live chat decision). Obj. 2 promises auto-removal of near-expiry stock (REQ066 fix). Obj. 3 promises exportable daily/monthly reports with batch + expiry (Reports module). | Both | High | -
Objectives / evaluation | p.5-6, 21-24 | Obj. 4 evaluates with TAM + ISO/IEC 25010, but there is no questionnaire, respondent group, sampling, scale, or statistical treatment yet. The final paper needs the instrument and a results chapter. | Paper | High | L
Scope | p.6 | 'Intended to serve retail customers, wholesale clients, branch staff, and main office management': wholesale clients and the main office never log in. Reword to 'staff record wholesale transactions; reports are submitted to the main office'. | Paper | Low | S
Scope | p.7 | 'Automated daily sales and inventory reports are generated': depends on the Reports module. | System | High | -
Scope | p.7 | AI live chat bullet: live chat decision. | Decision | High | -
Limitations | p.7 | 'Retail item exchanges ... coordinated through live chat': if chat is cut, change this to phone/Messenger. | Decision | Med | S
Limitations | p.7 | Add new limitations if decided: hosting/deployment, live chat/AI, real-time refresh, OpenAI cost. | Decision | Med | S
Comparative Analysis | p.18 | The three compared systems are named but not cited in that section: J1TEK = Binag et al. (2024), Online Transporter = Llorente et al. (2022), Bandung FEFO = Malasari & Sudrajat (2023). Binag and Llorente are in the reference list but cited nowhere in the text. | Paper | Med | S
Comparative Analysis | p.18 | The proposed system gets a tick for 'AI-powered live chat'; keep only if chat is built. | Decision | High | S
Theoretical Framework | p.22-23 | Mentions 'instantaneous push notifications for near-expiry supplies'; the system has an in-app notification bell, not push notifications. Reword. | Paper | Low | S
Theoretical Framework | p.24 | 'Only authorized branch managers can ... override automated inventory counts': needs the REQ061 fix (Branch Manager-only reconciliation finalize). | System | Med | S
Conceptual Framework (Input) | p.25 | Says wholesale buyers' info is captured during account registration and that wholesale purchase orders are submitted through the platform. Wholesale buyers don't register or order online; staff record them. | Paper | Med | S
Conceptual Framework (Output) | p.27 | 'Terms and Conditions remain available throughout the session': footer Privacy/Terms links are dead. Link them to the existing legal text. | System | Med | S
Methodology: sprint plan | p.32 | Phase 4 (customer side) lists the 'one-click copy feature for delivery details' under My Orders; that's an admin Delivery feature (also listed in Phase 6). Remove it from Phase 4. | Paper | Low | S
Methodology: sprint plan | p.30-35 | Phases promise features that aren't built (device OTP, notifications by email, thermal printing, live chat, reports). Align with final decisions. | Paper | Med | S
Methodology: Deployment | p.30 | 'Deployed in a controlled environment using actual client data': not done yet. Decide hosting, then either do it or reword. | Decision | Med | -
Technical Background | p.35 | Say 'Cloud Firestore' instead of 'real-time database', and Cloudinary instead of Firebase cloud storage for images. | Paper | Low | S
Technical Background | p.35-36 | EmailJS listed for order confirmations and password reset links: password reset is Firebase Auth; order emails depend on REQ039. | Paper | Low | S
Technical Background | p.35-36 | Chart.js listed for 'inventory movement data': dashboard charts are sales only (inventory uses count tiles). Reword or add an inventory chart. | Paper | Low | S
Technical Background | p.35, 37 | DataTable listed; tables are custom-built. Remove or reword. | Paper | Low | S
Technical Background | p.35, 37 | Netlify listed for hosting with continuous integration; nothing is deployed (Netlify blocked by billing). Depends on the hosting decision. | Decision | Med | S
Technical Background: Software | p.36-38 | Missing tools actually used: Cloudinary (images), Choices.js (searchable dropdowns), Bootstrap Icons, Google Fonts (Roboto), Git/GitHub (version control), Node.js http-server (local serving). | Paper | Low | S
Technical Background: Software | p.38 | Canva is listed for mockups, but the Gantt chart says 'Creation of Figma'. Use one tool name. | Paper | Low | S
Technical Background | p.35 | States the AI assistant won't give medical advice: keep only if chat is built. | Decision | Low | S
Modules: Staff roles | p.45-46 | Lists 'void authorization' for Branch Manager and Technical Staff: needs the void feature. 'Sales Staff: product catalog viewing only': see REQ121 decision. | Both | Med | S
Modules: Price Management | p.42 | 'Allows price locking': the lock is the Branch Manager-only rule (no separate lock switch). Reword, or add a lock toggle. | Paper | Low | S
System roles | - | The system also has a legacy 'Administrator' role that the paper never mentions. Hide it from the UI or document it. | System | Low | S
Wireframes (Figs 2.16-2.21) | p.92-95 | Not compared yet. Replace with real screenshots, or keep them labelled as early wireframes. | Paper | Low | S
Calendar of Activities | p.96-98 | Lists a 'Fifth Interview', but the appendices only have four transcripts (J-M). Add the transcript and proof, or remove the row. | Paper | Med | S
Calendar of Activities | p.96-98 | Month header has no year. Update the bars to actual dates. The webapp branch history starts 2026-08-31 (earlier work isn't in this git history), so the team needs to fill earlier dates. | Paper | Med | S
Calendar of Activities | p.97-98 | Add rows for work actually done (POS, inventory, payment verification, wholesale, reports, testing) and mark 'System Deployment' per the hosting decision. | Paper | Low | S
Budgetary Estimate | p.99 | Total ₱31,790.08 checks out. Missing: Cloudinary (free), OpenAI API (pay-per-use, if chat is built), thermal printer (if printing is in scope). | Paper | Low | S
Budgetary Estimate | p.99 | Domain name ₱841.08 and Firebase Blaze ₱200: keep only if actually bought/used. Netlify is listed as free, but deployment was blocked by billing; make these consistent. | Paper | Low | S
References | p.100 | Davis reference is written 'Fred D. Davis. (1989)'; APA is 'Davis, F. D. (1989).' | Paper | Low | S
References | p.10 / refs | 'The Generics Pharmacy (TGP) Sumulong Case Study (2024)' is cited without an author; check the APA author/organization format. | Paper | Low | S
References | p.17 / refs | Sardjono et al. (2023) is described as an Agile-based study, but its listed title is about Track and Trace in Pharma 4.0. Verify the source matches the summary. | Paper | Low | S
Appendices | p.124 | List of Appendices says 'PayMongo Pricing' / 'Lalamove API Instruction'; the appendix pages say 'PayMongo Pricing Limitation' / 'Lalamove API Limitation'. Match titles. | Paper | Low | S
Table of Contents / List of Figures | p.iv-vi | Regenerate page numbers after all edits. | Paper | Low | S
Client items | - | Get from the client: the QR Ph image, the sales invoice format, and the store details for the footer (hotline, email, hours, address, FDA LTO No. - fill js/store-info.js); have them review the Terms/Privacy text. Ask them: are all sales VAT-exempt (sample shows VATable 0.00), is pay-in/pay-out used, who tracks credit collections, which categories to use, may we load the real catalog for the demo? | Client | High | S

## Figures
Figure | Title | Image | Review
2.2 | Overall Use Case Diagram | Received | Reviewed
2.3 | Use Case: Platform Access and Account Management | Received | Reviewed
2.4 | Use Case: Customer Ordering and Purchase | Received | Reviewed
2.5 | Use Case: Inventory Management | Received | Reviewed
2.6 | Use Case: Order Processing and Sales Operations | Received | Reviewed
2.7 | Use Case: Administrative Controls | Received | Reviewed
2.8 | Activity: Login Process | Received | Reviewed
2.9 | Activity: Account Registration | Received | Reviewed
2.10 | Activity: Customer Purchasing | Received | Reviewed
2.11 | Activity: Payment Verification and Order Processing | Received | Reviewed
2.12 | Activity: Inventory Management | Received | Reviewed
2.13 | Activity: Wholesale Order Processing | Received | Reviewed
2.14 | Activity: Walk-in Order Processing (POS) | Received | Reviewed
2.15 | Activity: Wholesale Exchange Processing | Received | Reviewed
2.16-2.21 | Wireframes | Not requested | Optional - send if you want UI compared to wireframes