## Summary
Checks | 18
Pass | 0
Pass with note | 0
Fail | 0
Skipped | 0
Not run | 18
Ready for go-live? | Not yet - checks still to run

## Read Me
AMSON - Re-test after fixes (very quick)
18 checks: the fixes from the first test run plus the main jobs not tested yet. About 1 hour for one person, or about 30 minutes split between two (X01-X09 and X10-X18). Test on https://amsonpharma.web.app.
How to mark
Pass - works. Pass with note - works but something small looks off (write it in Notes). Fail - doesn't work (write what happened). Skipped - couldn't test (say why).
A 'Pass with note' is fine for go-live; only a 'Fail' needs fixing first. Send any Fail with its number (e.g. Q12) and what you saw.
Before you start
- Close every tab of the site first, then open it fresh (so the new version loads). Use a separate browser or profile per role.
- Have 2-3 products with stock, including one Rx product (X14 adds stock).
- Afterwards, clear the test data from Settings -> Clear Test Data (before November 15).
The longer plans are AMSON-Test-Plan-Quick.xlsx (35 checks) and AMSON-Test-Plan.xlsx (490 checks).

## Checks
# | Area | Log in as | Do this | Should happen | Req | Result | Tester | Notes
X01 | Tabs & login | Guest | Open the shop in 3 tabs at once: Home, Products, and one product page. | All 3 tabs show products (none stay empty). | REQ009 | Not run
X02 | Tabs & login | Customer | Log in WITHOUT 'Remember me' and open a new tab. Then close the browser completely and open the site again. | New tab is still logged in. After reopening the browser you're logged out (Login button shows). | REQ003 | Not run
X03 | Tabs & login | Customer | Log in WITH 'Remember me', close the browser completely, open the site again. | Still logged in. | REQ003 | Not run
X04 | Tabs & login | Branch Manager | While logged in as staff, open the shop home page. | A dark 'staff account' bar with Go to Dashboard and Log out; no customer menu or cart actions. | REQ043 | Not run
X05 | Tabs & login | Sales Staff | Type admin/dashboard.html in the address bar. | Only a spinner, then 'no access' and back to POS - the dashboard is never visible. | REQNF011 | Not run
X06 | Shop | Guest | Add an Rx product and a normal product to the cart, then click Proceed to Checkout and log in. | After login you land back on Checkout with the cart kept. Red 'Rx' tag next to the Rx item in cart and checkout. | REQ014, REQ021 | Not run
X07 | Shop | Customer | Place a normal (non-Rx) order: address, schedule, payment screenshot + reference no. | 'Pending Verification' in My Orders; bell + email confirm it. | REQ017-030 | Not run
X08 | Orders (staff) | Technical Staff | Online Orders tab: click the eye on that order. Then approve it in Payment Verification. | Pop-up shows contact, address, items, total. No 'no longer in the catalog' warning; approved with an SI No.; stock goes down. | REQ094-102 | Not run
X09 | Orders (staff) | Technical Staff | Put another order On Hold (Underpayment). As the customer, LOGGED OUT, click the link in the email. | Login page, then straight to that order (not 'couldn't find'); resubmitting works. | REQ097-098 | Not run
X10 | Orders (staff) | Technical Staff | Approve the Rx order; then click 'Mark as Picked Up' in the Online Orders tab. | Ready for Pick-up -> Picked Up; customer gets a notification. | REQ077-079 | Not run
X11 | Orders (staff) | Technical Staff | Book Delivery for the paid normal order with a share.lalamove.com link and the fee. | Status Dispatched; customer sees the tracking link and the fee in the email. | REQ103-105 | Not run
X12 | Chat | Guest | Chat: ask 'store hours?', then 'delivery fee?', then 'talk to staff'. | Hours answer (says 'not posted yet' until the client's hours are filled in); fee explained (set by Lalamove, paid to the rider); handed to staff. | REQ035-037 | Not run
X13 | POS | Sales Staff | Sell 2 items for cash and print the receipt, while Inventory is open in another tab or computer. | SI No. on the receipt; the Inventory quantity changes on its own. | REQ082, REQNF005 | Not run
X14 | Stock | Branch Manager | Receive Stock -> Upload Batch File (get the template from the ? button). | 'Stock received' pop-up listing each product; stock goes up. | REQ051-063 | Not run
X15 | Stock | Branch Manager | Create Purchase Order -> Upload Batch File; save it. Then receive it with one item short. | Rows filled from the file; 'Purchase order created' pop-up; short receipt -> Discrepancy + bell alert. | REQ053-057 | Not run
X16 | Wholesale & reports | Branch Manager | Process a wholesale order and download its invoice. Then Reports -> Daily Sales -> PDF. | Invoice shows buyer, batch and expiry; report totals match today's sales; dates MM/DD/YYYY. | REQ085-092, REQ111-115 | Not run
X17 | Admin | Branch Manager | Audit Log: search today's entries (price change, void, stock received, status changes). | Each shows Record / Before -> After / Reason where it applies. | REQ122-124 | Not run
X18 | Phone | Customer | On a phone: browse (swipe the category bar sideways), cart, checkout, My Orders. | Nothing runs off the screen; buttons tappable. | REQNF003 | Not run